## 1_Proposal_Approval
MASTER PLAN – E-COMMERCIAL BOOK STORE RELEASE 1.0 (Team 6 – Page Turners)
Proposal v0.5 – restructured into the class Master Plan layout (30/10) ¦ Prepared by Nguyễn Minh Chính (PO) with Hồ Du Tuấn Đạt ¦ Schedule 23/10 – 17/11/2026
Course | Software Project Management (72ITSE41503) – Final Project, Semester 261
Sponsor / Customer | Dr. Bùi Minh Phụng (lecturer) in the role of Ms. Le – approves the plan, issues the Change Request, signs UAT
Release 1.0 scope | F1 System administration · F2 Book management · F3 Book list · F4 Book details · F5 Search/filter [03 §2.2] – 18 backlog items (US-01…US-13, NFR-01…NFR-05)
Out of scope | Shopping cart, payment, social login → 10 items kept for Release 2 (R2-01…R2-10, sheet 3)
Minimum non-functional | Responsive · ≥ 30 sample books · list page < 2 s · client + server validation · hashed passwords · free hosting online until 17/11
Tools | Jira (space ECBS: board, Original Estimate, Completed Work) · GitHub repo (main/develop, reviewed PRs, tags) · Excel workbook · stack Next.js + PostgreSQL (Supabase) + Vercel
Effort & budget
A. PROPOSED SPRINT LEADER ROTATION (Option A – recommended)
Sprint | Dates | Sprint Leader | Product Owner | Sprint PM focus | Increment | Why this Leader | Submission / Review
Sprint 1 | Fri 23/10 – Thu 29/10 | Hồ Du Tuấn Đạt | Nguyễn Minh Chính | PMP v1.0 (7 parts), Product Backlog v1.0, Planning Poker, Release Plan, BAC, Sprint Planning 1; record CR-06 | F1 – System administration + hosting | Scrum Master in Lab 3 and the TA; owns the repo and the Jira site; built the F1 code | Due 23:59 Thu 29/10 · Review 1 + CCB: Fri 30/10
Sprint 2 | Fri 30/10 – Thu 05/11 | Nguyễn Minh Chính | Nguyễn Minh Chính | CR-06 in 5 steps + CCB, Weekly Status Report, risk register and issue log, F2/F3 test cases | F2 – Book management · F3 – Book list (+ CR-06 US-24 if approved) | 2-member rule: the PO leads Sprint 2 [03 §4.1]; the PO wrote the AC that the CR changes | Due 23:59 Thu 05/11 · Review 2: Fri 06/11
Sprint 3 | Fri 06/11 – Thu 12/11 | Hồ Du Tuấn Đạt | Nguyễn Minh Chính | Release v1.0 (tag + release notes), UAT script, EVM draft, F4/F5 test cases, regression F1–F3 | F4 – Book details · F5 – Search/filter (+ CR-06 US-25 if approved) | Second Sprint for the non-PO member [03 §4.1]; backend owner for search/filter and the release tag | Due 23:59 Thu 12/11 · Review 3 + UAT: Fri 13/11
Closure | Fri 13/11 – Tue 17/11 | Whole team | Nguyễn Minh Chính | Final Report (plan vs. actual, EVM), Lessons Learned, slides, demo video | Release 1.0 online until end of 17/11 | Not a Sprint – no Leader turn; Chính coordinates the Final Report | Final submission: 23:59 Sun 15/11 · Presentation: 07:00 Tue 17/11
B. OPTIONS COMPARED
Option | Sprint 1 | Sprint 2 | Sprint 3 | Pros | Cons / risks | Rating
A (recommended) | Hồ Du Tuấn Đạt | Nguyễn Minh Chính (PO) | Hồ Du Tuấn Đạt | Keeps the Lab 3 / TA roles (Chính PO, Đạt Scrum Master); Đạt, who owns the repo and Jira, leads the setup Sprint; the PO is the Leader when the CR is processed. | In Sprint 2 the PO and the Leader are the same person at the CCB → Đạt reviews the impact analysis before the CCB. | ★★
B | Nguyễn Minh Chính | Hồ Du Tuấn Đạt (PO) | Nguyễn Minh Chính | Chính leads twice and keeps the board, where he already did the TA Week 2 setup. | Changes the PO two weeks before the end; Đạt would have to take over the backlog and AC written by Chính; breaks continuity with Lab 3. | ★
With 2 members the rule allows only these two patterns: the PO leads Sprint 2, the other member leads Sprints 1 and 3 [03 §4.1].
C. DECISIONS FOR APPROVAL (choose in the 'Status' column – yellow cells)
# | Item | Proposal |  | Rationale |  | Status | Reviewer notes
1 | Leader rotation & PO | Option A: Đạt (S1) → Chính (S2) → Đạt (S3); PO = Chính, fixed, also a Developer. Recorded in plan/INPUTS.md §1 (30/10/2026). |  | Mandatory 2-member rule [03 §4.1]; continuity with Lab 3 and the TA. |  | Pending
2 | Product Backlog v1.0 | 30 items: 18 for Release 1.0 (US-01…US-13, NFR-01…NFR-05), 2 for CR-06 (US-24, US-25), 10 kept for Release 2 (R2-01…R2-10). GWT ACs and DoR in pm/backlog/. |  | Spec scope [03 §2.2]; ≥ 15 items; gap analysis [05 §1, §4]. |  | Pending
3 | Item allocation per Sprint | Reference plan: S1 F1 + hosting · S2 F2 + F3 (+ seed data, responsive) · S3 F4 + F5 + list < 2 s + release. |  | Matches the brief's reference Sprints [03 §2.2]; every Increment shown on the hosted URL. |  | Pending
4 | Capacity & budget |  |  | BAC = planned person-hours × 200,000 VND [03 §6.4]; same figures as PMP-3 §3.5–3.6. |  | Pending
5 | Estimation | SP only from Planning Poker with every round logged (sheet 8, BM01 format); expected velocity = PSP ÷ 3 until the actual Sprint 1 velocity exists. |  | Planning Poker evidence is graded (B4) and was missing last year [03 §8]. |  | Pending
6 | Change Request CR-06 | Logged in the Change Log; impact analysis with options A / B / C. Team recommendation: Option B (US-24 in S2, US-25 in S3; +12 h, +2,400,000 VND). Enters the plan only if approved → baseline v1.1. |  | 5-step CR process [03 §6.2 item 3]; pm/change/CR-06-impact-analysis.md. |  | Pending
7 | Scrum event calendar | Sprint Planning ≤ 45 min on the first day of each Sprint; Daily Scrum ≤ 10 min, logged (channel to confirm in plan/INPUTS.md §1); Review + Retro on Friday in class. |  | Timeboxes [03 §4.2]. |  | Pending
8 | Configuration management | Branches main ← develop ← feat/Pxx-…, docs/Pxx-…; every change by PR into develop, reviewed by the other member before merge; Conventional Commits + 'Refs: Pxx'; tags baseline-v1.0, baseline-v1.1 (if CR approved), v1.0. |  | No direct commits to main [03 §4.2]; criteria S5 and B7. PRs #1–#4 (30/10) were merged without review – corrected from Sprint 2. |  | Pending
9 | Sprint 1 recovery | On 30/10 the Sprint 1 package was not complete at 29/10 23:59 (issue I-01). F1 code is done and tested locally; hosting, Planning Poker, Jira hours and the manual test run are completed before Review 1; the actual S1 result is reported honestly and the allocation re-checked at Sprint Planning 2. |  | Late penalty −10 % per 5 h [03 §4.2]; unfinished work returns to the backlog [Rubric 1, S2]. |  | Pending
Approved:
D. VERSION HISTORY
Version | Date | Author | Changes
0.1 | 30/10/2026 | Chính (drafted with Claude) | First draft as a Word document: schedule, milestones, Leader rotation, item allocation, velocity/PSP/BAC formulas.
0.2 | 30/10/2026 | Chính (drafted with Claude) | Workbook: WBS with owner, proposed hours and dates per task; BAC from the WBS; allocation; timeline; RACI; submission schedule; decisions for approval. vs. TA Work Plan: 2-week Sprint → three 1-week Sprints; scope → Release 1.0 (F1–F5).
0.3 | 30/10/2026 | Chính (drafted with Claude) | Capacity 28 h/person/Sprint (PO assumption); Planning Poker log in the BM01 format.
0.4 | 30/10/2026 | Chính (drafted with Claude) | Reorganised into the class Master Plan layout (proposal & approval, master schedule, item allocation, release plan, responsibilities, deliverables) + timeline and Planning Poker sheets; leader options compared.
0.5 | 30/10/2026 | Chính (drafted with Claude) | Aligned with the repository (PMP-3 v1.1-draft): backlog IDs of Product Backlog v1.0; Sprint 1 = S1_Backlog (14 tasks, 48 h); Sprint 2 = S2_Backlog draft; capacity 20 h/person/Sprint (40 h), BAC 24,000,000 VND; expected velocity = PSP ÷ 3; CR-06 Option B (+12 h).
0.6 | 30/10/2026 | Chính (drafted with Claude) | Sheet 8 filled with PO estimates from AI-suggested values (no voting rounds): PSP = 55 SP (S1 18 · S2 24 · S3 13), CR-06 +7 SP; expected velocity ≈ 18.3 SP/Sprint.
Legend: yellow cells = reviewer / team input. Story Points stay empty until the Planning Poker session; capacity and effort are planning assumptions, not actual hours (actual hours come from Jira Completed Work).

## 2_MasterSchedule
MASTER SCHEDULE & WBS 23/10 – 17/11/2026
Sprint 1 = pm/sprints/S1/sprint-backlog.md (14 tasks, 48 h); Sprint 2 = pm/sprints/S2/sprint-backlog.md (draft); Sprint 3 and closure = proposal. Tasks ≤ 1 person-day; 'Both' counted half per member. Status as of 30/10/2026.
WBS | Phase | Work package / task | Owner | Effort (h) | Output / evidence | Status | Planned start | Planned finish
1 | Sprint 1 | SPRINT 1 (Fri 23/10 – Thu 29/10) – Plan baseline & F1 ¦ Leader: Hồ Du Tuấn Đạt |  |  | Sprint Goal: users can register, log in and log out; an administrator can create and lock accounts; non-admins are blocked from admin functions on the server (F1 on the hosted URL).
1.1 | Sprint 1 | Project management – PMP v1.0 baseline (S1_Backlog S1-T01…T05, T13, T14)
S1-T01 | Sprint 1 | Product Backlog v1.0 + Definition of Ready (GWT ACs) | Nguyễn Minh Chính | 4 | pm/backlog/product-backlog.md | In Progress | 2026-10-23 | 2026-10-26
S1-T02 | Sprint 1 | Planning Poker session + Release Plan + BAC | Nguyễn Minh Chính | 2 | Planning Poker log; this workbook | In Progress | 2026-10-26 | 2026-10-27
S1-T03 | Sprint 1 | PMP v1.0 parts 1, 3, 5, 6 | Hồ Du Tuấn Đạt | 6 | pm/pmp/01, 03, 05, 06 | In Progress | 2026-10-24 | 2026-10-28
S1-T04 | Sprint 1 | PMP v1.0 parts 2, 4, 7 | Nguyễn Minh Chính | 4 | pm/pmp/02, 04, 07 | In Progress | 2026-10-24 | 2026-10-28
◆ | Sprint 1 | ◆ Tue 27/10 in class: Change Request CR-06 received | Nguyễn Minh Chính | 0 | CR-06 form | Done | 2026-10-27 | 2026-10-27
S1-T05 | Sprint 1 | CR-06: Change Log entry + impact analysis + CCB options | Nguyễn Minh Chính | 3 | pm/change/ | In Progress | 2026-10-27 | 2026-10-29
S1-T13 | Sprint 1 | Workbook c2, Sprint Report c3, submission | Hồ Du Tuấn Đạt | 3 | deliverables/S1/ | In Progress | 2026-10-28 | 2026-10-29
S1-T14 | Sprint 1 | Review/Retro 1 preparation | Hồ Du Tuấn Đạt | 2 | pm/sprints/S1/review-retro.md | In Progress | 2026-10-29 | 2026-10-29
1.2 | Sprint 1 | Development – F1 (S1_Backlog S1-T06…T11)
S1-T06 | Sprint 1 | Scaffold app, DB schema, deploy skeleton (NFR-03) | Hồ Du Tuấn Đạt | 4 | app/; hosted URL | In Progress | 2026-10-23 | 2026-10-24
S1-T07 | Sprint 1 | US-01, NFR-01 Register: form, client + server validation, bcrypt | Hồ Du Tuấn Đạt | 4 | Merged code + tests | Done | 2026-10-24 | 2026-10-26
S1-T08 | Sprint 1 | US-02 Log in / log out, sessions, locked-account check | Hồ Du Tuấn Đạt | 3 | Merged code + tests | Done | 2026-10-26 | 2026-10-27
S1-T09 | Sprint 1 | US-03 Admin account list, create account with role, lock/unlock | Nguyễn Minh Chính | 5 | Merged code + tests | Done | 2026-10-26 | 2026-10-28
S1-T10 | Sprint 1 | US-04 Server-side role guard, 403 page, hide admin menu | Hồ Du Tuấn Đạt | 2 | Merged code + tests | Done | 2026-10-27 | 2026-10-28
S1-T11 | Sprint 1 | NFR-04 (base) Responsive base layout and styles | Nguyễn Minh Chính | 3 | Merged code + screenshots | Done | 2026-10-27 | 2026-10-28
1.3 | Sprint 1 | Testing – F1 (S1_Backlog S1-T12)
S1-T12 | Sprint 1 | F1 test cases (24) + automated tests + run (manual run on hosted URL pending) | Nguyễn Minh Chính | 3 | pm/sprints/S1/test-cases-F1.md | In Progress | 2026-10-28 | 2026-10-29
M3 | Sprint 1 | ◆ SPRINT 1 SUBMISSION – 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | 0 | Upload each file separately to E-learning; no zip |  | 2026-10-29 | 2026-10-29
2 | Sprint 2 | SPRINT 2 (Fri 30/10 – Thu 05/11) – Execution, monitoring & change control ¦ Leader: Nguyễn Minh Chính (PO) |  |  | Sprint Goal (proposal): admins manage books (hide, price > 0), categories and authors; customers browse a responsive grid of ≥ 30 books, 12 per page, newest first; if CR-06 is approved, Staff gets 403 on delete and account management.
2.1 | Sprint 2 | Scrum events & project management (S2_Backlog draft)
S2-T01 | Sprint 2 | Review & Retro 1 (in class) + Sprint Planning 2 (≤ 45 min) → S2_Backlog → Jira | Both | 1.5 | S2_Backlog; Jira Sprint 2 | To Do | 2026-10-30 | 2026-10-30
S2-T02 | Sprint 2 | Daily Scrum S2 (≤ 10 min/day, logged) + daily board update | Both | 1 | Daily log | To Do | 2026-10-30 | 2026-11-05
S2-T03 | Sprint 2 | CCB decision; rebaseline backlog, AC, Release Plan, risk register; tag baseline-v1.1 if approved | Nguyễn Minh Chính | 2 | Rebaselined plan + tag | To Do | 2026-10-30 | 2026-10-31
S2-T04 | Sprint 2 | Weekly Status Report; risk register and issue log update | Nguyễn Minh Chính | 2 | Status report | To Do | 2026-11-03 | 2026-11-05
S2-T05 | Sprint 2 | c4_ChangeRequest_CR01.docx | Nguyễn Minh Chính | 2 | c4 form | To Do | 2026-11-02 | 2026-11-05
S2-T06 | Sprint 2 | c2_SprintBacklog_S2, c3_SprintReport_S2, c0_Eval_S2, upload | Nguyễn Minh Chính | 1.75 | c2, c3, c0 – Sprint 2 | To Do | 2026-11-04 | 2026-11-05
2.2 | Sprint 2 | Development – F2 and F3
S2-T07 | Sprint 2 | Data model: books, categories, authors, hidden flag; migration | Hồ Du Tuấn Đạt | 2 | Merged code | To Do | 2026-10-31 | 2026-10-31
S2-T08 | Sprint 2 | US-08 Manage categories (screens + API + validation) | Nguyễn Minh Chính | 2 | Reviewed PR | To Do | 2026-10-31 | 2026-11-01
S2-T09 | Sprint 2 | US-09 Manage authors (screens + API + validation) | Nguyễn Minh Chính | 2 | Reviewed PR | To Do | 2026-11-01 | 2026-11-02
S2-T10 | Sprint 2 | US-05 Add book: form, cover image, price > 0, client + server validation | Hồ Du Tuấn Đạt | 3 | Reviewed PR | To Do | 2026-10-31 | 2026-11-01
S2-T11 | Sprint 2 | US-06 Edit book | Hồ Du Tuấn Đạt | 1.5 | Reviewed PR | To Do | 2026-11-01 | 2026-11-02
S2-T12 | Sprint 2 | US-07 Hide book (soft delete) | Hồ Du Tuấn Đạt | 1 | Reviewed PR | To Do | 2026-11-02 | 2026-11-02
S2-T13 | Sprint 2 | NFR-02 Seed ≥ 30 sample books | Hồ Du Tuấn Đạt | 1.5 | Seed script | To Do | 2026-11-02 | 2026-11-03
S2-T14 | Sprint 2 | US-10 Book grid: cover, title, author, price; 12 per page; newest first | Nguyễn Minh Chính | 3 | Reviewed PR | To Do | 2026-11-02 | 2026-11-03
S2-T15 | Sprint 2 | NFR-04 Responsive check of new pages (360 / 768 / 1280 px) | Nguyễn Minh Chính | 1 | Screenshots | To Do | 2026-11-04 | 2026-11-04
2.3 | Sprint 2 | CR-06 Option B – Sprint 2 part (only if the CCB approves)
S2-T16 | Sprint 2 | C1 staff role + migration, audit columns (US-24) | Hồ Du Tuấn Đạt | 1 | Reviewed PR | To Do | 2026-10-31 | 2026-10-31
S2-T17 | Sprint 2 | C2 permission matrix on the server – 403 on delete and account management (US-24) | Hồ Du Tuấn Đạt | 2 | Reviewed PR | To Do | 2026-11-01 | 2026-11-02
S2-T18 | Sprint 2 | C3 Admin assigns/changes role incl. Staff (US-03 rework) | Hồ Du Tuấn Đạt | 1.5 | Reviewed PR | To Do | 2026-11-02 | 2026-11-03
S2-T19 | Sprint 2 | C4 Staff access to book/category/author screens; hide Delete (US-24) | Hồ Du Tuấn Đạt | 2 | Reviewed PR | To Do | 2026-11-03 | 2026-11-04
S2-T20 | Sprint 2 | C6 (part) CR test cases + F1 regression | Hồ Du Tuấn Đạt | 1 | Test results | To Do | 2026-11-04 | 2026-11-05
S2-T21 | Sprint 2 | C7 CR documentation in the baseline | Nguyễn Minh Chính | 1 | Updated docs | To Do | 2026-11-04 | 2026-11-05
2.4 | Sprint 2 | Testing – F2 and F3
S2-T22 | Sprint 2 | F2/F3 test cases from AC (≥ 1 per AC) | Nguyễn Minh Chính | 2 | Test cases F2, F3 | To Do | 2026-11-02 | 2026-11-04
S2-T23 | Sprint 2 | Run F2/F3 test cases on the hosted URL + F1 regression; record results and defects | Hồ Du Tuấn Đạt | 2 | Test results | To Do | 2026-11-04 | 2026-11-05
M5 | Sprint 2 | ◆ SPRINT 2 SUBMISSION – 23:59 Thu 05/11 | Nguyễn Minh Chính | 0 | Upload each file separately to E-learning; no zip |  | 2026-11-05 | 2026-11-05
3 | Sprint 3 | SPRINT 3 (Fri 06/11 – Thu 12/11) – Complete Release 1.0 & acceptance ¦ Leader: Hồ Du Tuấn Đạt |  |  | Sprint Goal (proposal): customers open book details and search/filter by title, author, category and price range together with pagination; F1–F3 pass regression; v1.0 tagged and ready for UAT.
3.1 | Sprint 3 | Scrum events & release
S3-T01 | Sprint 3 | Review & Retro 2 (in class) + Sprint Planning 3 with actual S2 velocity | Both | 1.5 | S3_Backlog; Jira Sprint 3 | To Do | 2026-11-06 | 2026-11-06
S3-T02 | Sprint 3 | Daily Scrum S3 + daily board update | Both | 1 | Daily log | To Do | 2026-11-06 | 2026-11-12
S3-T11 | Sprint 3 | UAT script mapped to every AC (incl. CR-06 if approved) | Nguyễn Minh Chính | 3 | pm/uat/uat-script.md | To Do | 2026-11-09 | 2026-11-12
S3-T12 | Sprint 3 | Release v1.0: PR develop → main, tag v1.0, release notes | Hồ Du Tuấn Đạt | 1.5 | Tag v1.0; release notes | To Do | 2026-11-11 | 2026-11-12
S3-T13 | Sprint 3 | EVM draft (PV, EV, AC, SV, CV, SPI, CPI, EAC, ETC) from Jira hours | Nguyễn Minh Chính | 1.5 | EVM sheet (draft) | To Do | 2026-11-10 | 2026-11-12
S3-T14 | Sprint 3 | c2_SprintBacklog_S3, c3_SprintReport_S3, c5_UAT, c0_Eval_S3, upload | Hồ Du Tuấn Đạt | 2 | c2, c3, c5, c0 – Sprint 3 | To Do | 2026-11-11 | 2026-11-12
3.2 | Sprint 3 | Development – F4 and F5 (+ CR-06 Option B, Sprint 3 part)
S3-T03 | Sprint 3 | US-11 Book details page; unknown ID → friendly message; Back returns to the same list page | Nguyễn Minh Chính | 4 | Reviewed PR | To Do | 2026-11-07 | 2026-11-09
S3-T04 | Sprint 3 | US-12 Search by title or author | Hồ Du Tuấn Đạt | 3 | Reviewed PR | To Do | 2026-11-07 | 2026-11-08
S3-T05 | Sprint 3 | US-13 Filter by category and price range, combined with search and pagination | Hồ Du Tuấn Đạt | 4 | Reviewed PR | To Do | 2026-11-08 | 2026-11-10
S3-T06 | Sprint 3 | NFR-05 Measure list load < 2 s with ≥ 30 books; fix if needed | Hồ Du Tuấn Đạt | 2 | Timing evidence | To Do | 2026-11-10 | 2026-11-11
S3-T07 | Sprint 3 | C5 'Last updated by … at …' (US-25, only if CR-06 approved) | Hồ Du Tuấn Đạt | 1.5 | Reviewed PR | To Do | 2026-11-07 | 2026-11-08
S3-T08 | Sprint 3 | C6 (rest) CR test cases + regression (only if CR-06 approved) | Nguyễn Minh Chính | 2 | Test results | To Do | 2026-11-09 | 2026-11-10
3.3 | Sprint 3 | Testing – F4 and F5
S3-T09 | Sprint 3 | F4/F5 test cases from AC | Nguyễn Minh Chính | 2 | Test cases F4, F5 | To Do | 2026-11-08 | 2026-11-10
S3-T10 | Sprint 3 | Run F4/F5 test cases + regression F1–F3; record results and defects | Hồ Du Tuấn Đạt | 3 | Test results; defect log | To Do | 2026-11-10 | 2026-11-11
S3-T15 | Sprint 3 | Defect-fixing buffer | Nguyễn Minh Chính | 3.5 | Fixed defects | To Do | 2026-11-10 | 2026-11-12
M7 | Sprint 3 | ◆ RELEASE v1.0 + SPRINT 3 SUBMISSION – 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | 0 | Upload each file separately to E-learning; no zip |  | 2026-11-12 | 2026-11-12
4 | Closure | CONSOLIDATION & CLOSURE (Fri 13/11 – Tue 17/11) ¦ Whole team |  |  | Goal: Release 1.0 accepted at UAT and online until 17/11; final package submitted on time; every member presents.
4.1 | Closure | Acceptance and hand-over
4.1.1 | Closure | ◆ Review 3 + UAT with the customer; acceptance record | Both | 2 | Signed acceptance record | To Do | 2026-11-13 | 2026-11-13
4.1.2 | Closure | Final hosting check, demo accounts (admin, customer), closure data | Hồ Du Tuấn Đạt | 2 | URL; demo accounts; closure data | To Do | 2026-11-13 | 2026-11-14
4.2 | Closure | Closure documents and presentation
4.2.1 | Closure | Final Report: plan vs. actual, EVM, risks & changes, closure checklist, Lessons Learned ≥ 5, AI declaration | Nguyễn Minh Chính | 4 | c6_FinalReport.docx | To Do | 2026-11-13 | 2026-11-15
4.2.2 | Closure | PMP Final + Workbook Final (EVM sheet) | Hồ Du Tuấn Đạt | 3 | c1_ProjectPlan_Final, c2_SprintBacklog_Final | To Do | 2026-11-13 | 2026-11-15
4.2.3 | Closure | Slides (font ≥ 20 pt) + demo video ≤ 3 min (pass and fail AC) | Both | 4 | c6_Slides; video link | To Do | 2026-11-14 | 2026-11-15
4.2.4 | Closure | Final submission + one Eval360 file per member | Both | 1 | All final files | To Do | 2026-11-15 | 2026-11-15
4.2.5 | Closure | Rehearsal; keep the website online until the end of 17/11 | Both | 2 | Rehearsal notes | To Do | 2026-11-16 | 2026-11-17
M10 | Closure | ◆ FINAL PRESENTATION – 07:00 Tue 17/11 | Both | 0 |  |  | 2026-11-17 | 2026-11-17
Total effort Sprints 1–3 (h) – basis of BAC
Closure effort (h) – after Sprint 3, outside BAC (PV is defined over N = 3 Sprints)

## 3_ItemAllocation
PRODUCT BACKLOG ALLOCATION PER SPRINT (Product Backlog v1.0)
IDs and stories as in pm/backlog/product-backlog.md (v1.0-draft, 30 items; v0 = TA backlog, 23 items, 99 SP). SP = final Planning Poker result from sheet 8 (empty until the session is held).
ID | Feature | Epic | User Story (short) | SP | MoSCoW | Sprint | Main developer | Change vs. backlog v0 (v0 SP in brackets)
US-01 | F1 | EP-01 User Accounts | Visitor registers with name, email and password (signs in as Customer) |  | Must | Sprint 1 | Hồ Du Tuấn Đạt | Kept – v0 US-01; email confirmation dropped, hashing + validation ACs added [v0: 3 SP]
US-02 | F1 | EP-01 User Accounts | Registered user logs in and logs out |  | Must | Sprint 1 | Hồ Du Tuấn Đạt | Kept – v0 US-02; password reset moved to Release 2 [v0: 3 SP]
US-03 | F1 | EP-01 User Accounts | Administrator creates accounts with a role and locks/unlocks accounts |  | Must | Sprint 1 | Nguyễn Minh Chính | Rewritten – v0 US-03 (Store Manager/Staff roles removed) [v0: 5 SP]
US-04 | F1 | EP-01 User Accounts | Admin functions blocked on the server for anyone who is not an administrator |  | Must | Sprint 1 | Hồ Du Tuấn Đạt | New [new]
NFR-01 | F1 | EP-08 Quality (NFR) | Passwords stored as hashes; every form validated on client and server |  | Must | Sprint 1 | Hồ Du Tuấn Đạt | New [new]
NFR-03 | All | EP-08 Quality (NFR) | Site hosted on a free public URL until 17/11/2026 |  | Must | Sprint 1 | Hồ Du Tuấn Đạt | New [new]
US-05 | F2 | EP-03 Book Management | Administrator adds a book (title, author, category, price > 0, description, cover, stock) |  | Must | Sprint 2 | Hồ Du Tuấn Đạt | Changed – v0 US-08 [v0: 5 SP]
US-06 | F2 | EP-03 Book Management | Administrator edits a book |  | Must | Sprint 2 | Hồ Du Tuấn Đạt | Kept – v0 US-09 [v0: 3 SP]
US-07 | F2 | EP-03 Book Management | Administrator deletes (hides) a book without losing its record |  | Must | Sprint 2 | Hồ Du Tuấn Đạt | Kept – v0 US-10 [v0: 2 SP]
US-08 | F2 | EP-03 Book Management | Administrator manages categories |  | Must | Sprint 2 | Nguyễn Minh Chính | New [05 #5] [new]
US-09 | F2 | EP-03 Book Management | Administrator manages authors |  | Must | Sprint 2 | Nguyễn Minh Chính | New [05 #5] [new]
NFR-02 | F2/F3 | EP-08 Quality (NFR) | At least 30 sample books loaded |  | Must | Sprint 2 | Hồ Du Tuấn Đạt | New – v0 task T-16 [new]
US-10 | F3 | EP-02 Book Catalog | Customer browses a grid of 12 books per page, newest first |  | Must | Sprint 2 | Nguyễn Minh Chính | Changed – v0 US-05 (20 → 12 per page) [v0: 3 SP]
NFR-04 | F3 | EP-08 Quality (NFR) | Every page works on phone, tablet and desktop |  | Must | Sprint 2 | Nguyễn Minh Chính | Kept – v0 US-21 [v0: 5 SP]
US-11 | F4 | EP-02 Book Catalog | Customer opens a book's detail page and goes back to the same list page |  | Must | Sprint 3 | Nguyễn Minh Chính | Changed – v0 US-07 (+ friendly not-found, Back keeps page) [v0: 3 SP]
US-12 | F5 | EP-02 Book Catalog | Customer searches by title or author |  | Must | Sprint 3 | Hồ Du Tuấn Đạt | Split from v0 US-06 (v0 SP is for the whole of US-06) [v0: 5 SP]
US-13 | F5 | EP-02 Book Catalog | Customer filters by category and price range with search and pagination |  | Must | Sprint 3 | Hồ Du Tuấn Đạt | Split from v0 US-06 [new]
NFR-05 | F3/F5 | EP-08 Quality (NFR) | Book list loads in under 2 seconds |  | Must | Sprint 3 | Hồ Du Tuấn Đạt | New – from a v0 US-06 AC [new]
US-24 | F1, F2 | EP-01 User Accounts | CR-06: Store Staff adds/edits books, manages categories and authors; cannot delete books or manage accounts |  | CCB decides | CR-06 | Hồ Du Tuấn Đạt | Change Request – Option B: Sprint 2 [new]
US-25 | F2 | EP-03 Book Management | CR-06: each book shows 'Last updated by … at …' |  | CCB decides | CR-06 | Hồ Du Tuấn Đạt | Change Request – Option B: Sprint 3 [new]
R2-01 | — | Release 2 | Customer profile and shipping addresses |  | Won't (R1.0) | Future |  | v0 US-04 – supports checkout, out of scope [03 §2.2] [v0: 2 SP]
R2-02 | — | Release 2 | Shopping cart |  | Won't (R1.0) | Future |  | v0 US-11 – out of scope [03 §2.2] [v0: 5 SP]
R2-03 | — | Release 2 | Checkout and online payment |  | Won't (R1.0) | Future |  | v0 US-12 – out of scope [03 §2.2] [v0: 8 SP]
R2-04 | — | Release 2 | Order history and tracking |  | Won't (R1.0) | Future |  | v0 US-13 – depends on checkout [v0: 3 SP]
R2-05 | — | Release 2 | Staff processes orders |  | Won't (R1.0) | Future |  | v0 US-14 – depends on checkout [v0: 5 SP]
R2-06 | — | Release 2 | Promotions and discount codes |  | Won't (R1.0) | Future |  | v0 US-15/16 (5 + 3) – depends on checkout [v0: 8 SP]
R2-07 | — | Release 2 | Multi-store inventory and in-store pickup |  | Won't (R1.0) | Future |  | v0 US-17/18 (8 + 5) – not in F1–F5 [v0: 13 SP]
R2-08 | — | Release 2 | Ratings and reviews |  | Won't (R1.0) | Future |  | v0 US-19 – not in F1–F5 [v0: 5 SP]
R2-09 | — | Release 2 | Wishlist |  | Won't (R1.0) | Future |  | v0 US-20 – not in F1–F5 [v0: 2 SP]
R2-10 | — | Release 2 | Brand style guide, recommendations, password reset by email |  | Won't (R1.0) | Future |  | v0 US-22, US-23, US-02 reset (3 + 8 + –) – not in F1–F5 [v0: 11 SP]
Summary
|  |  | Sprint | SP | Items
Sprint 1
Sprint 2
Sprint 3
CR-06
|  |  | Future | —
Release 1.0 total (PSP) = Sprints 1–3
Total backlog items (required ≥ 15)

## 4_ReleasePlan
RELEASE PLAN, CAPACITY & BUDGET (BAC)
Same figures as pm/pmp/03-master-release-plan.md §3.5–3.6. Yellow = inputs; blue = sourced constants; all other cells are formulas.
Assumptions
Team members | 2 | Hồ Du Tuấn Đạt, Nguyễn Minh Chính
Hours / person / Sprint (planned capacity) | 20 | 4 focus h/day × 5 working days (Fri, Mon–Thu) – PMP-3 §3.5 scenario, adopted by the PO on 30/10/2026; Đạt to confirm (plan/INPUTS.md §2)
Number of Sprints (N) | 3 | Per the spec [03 §5]
Rate (VND / person-hour) | 200000 | Per the spec – AgileEVM [03 §6.4]
Team capacity per Sprint (h) |  | Members × hours per person
Expected velocity (SP / Sprint) |  | PSP ÷ 3 Sprints (PMP-3 §3.5); replaced by the ACTUAL velocity from Sprint Planning 2 on [03 §6.2 item 1]
Plan per Sprint
Sprint | Dates | Leader | Sprint Goal | Features | Planned SP | Capacity (h) | WBS planned effort (h) | Hours / SP | Cumulative PV (VND) | SP vs. velocity | Hours vs. capacity
Sprint 1 | 23/10 – 29/10 | Hồ Du Tuấn Đạt |  | F1 + hosting
Sprint 2 | 30/10 – 05/11 | Nguyễn Minh Chính (PO) |  | F2, F3 (+ CR-06 US-24 if approved)
Sprint 3 | 06/11 – 12/11 | Hồ Du Tuấn Đạt |  | F4, F5 (+ CR-06 US-25 if approved) + Release v1.0
Total
Sprint 1 planned 48 h against 40 h capacity: the overload is recorded, not hidden (S1_Backlog PO note, issue I-01). Sprints 2 and 3 are planned within capacity.
Baseline metrics
Metric | Value | Formula / note
BAC (VND) = planned person-hours of the release × rate |  | 40 h × 3 Sprints = 120 h × 200,000 VND (PMP-3 §3.6, plan)
PSP – total planned Story Points of Release 1.0 |  | PO estimates 30/10/2026, no voting rounds (sheet 8)
PSP matches sheet 3
WBS task hours Sprints 1–3 (cross-check) |  | Sum of task estimates; differs from 120 h because Sprint 1 was overloaded
Closure effort (h) – outside BAC |  | 13/11 – 17/11, after the 3 Sprints
Rebaseline after CR-06 (only if the CCB approves)
Item | Value | Source / note
CCB decision | Pending | Team recommendation: Option B (PO, 30/10/2026). Enter the Sponsor's decision after the CCB
CR-06 hours added | 12 | pm/change/CR-06-impact-analysis.md §2.2 – Option B: 8.5 h in S2 + 3.5 h in S3
BAC v1.1 (VND) |  | Baseline v1.0 is kept; v1.1 is added [03 §6.2 item 3]
PSP v1.1 (SP)
Note: Sprint Planning 2 and 3 use the ACTUAL velocity of the previous Sprint, not the expected figure [03 §6.2 item 1]. A 2-member team adjusts capacity and the plan, never the F1–F5 scope [03 §2.2].

## 5_Responsibilities
ROLES & DOCUMENT RESPONSIBILITIES
A = accountable (one per row) · R = does the work · C = consulted / reviews · I = informed
Item | Hồ Du Tuấn Đạt | Nguyễn Minh Chính | Notes
Scrum role | Developer; Sprint Leader S1, S3 | Product Owner + Developer; Sprint Leader S2 | Fixed PO, rotating Leader [03 §4.1]
PMP 1 – Project Charter | C | A/R | From Lab 1–2 (Chính was Project Lead / BA)
PMP 2 – Tailored Scrum process | A/R | C | From TA Process.docx
PMP 3 – Master / Release Plan | C | A/R | This workbook
PMP 4 – Quality plan (3-level DoD, metrics) | C | A/R | PO accepts Done items
PMP 5 – Risk management plan | A/R | C | Risks reviewed every Sprint
PMP 6 – Configuration management plan | A/R | C | Repo owner
PMP 7 – Communication plan | A/R | C | From Lab 1 §4 (Đạt) and Assign.xlsx
Product Backlog, AC, Definition of Ready | C | A/R | PO orders the backlog
Planning Poker (log + evidence) | R | A/R | Both vote; PO reads the stories
Sprint Backlog + Jira (each Sprint) | A/R in S1, S3 | A/R in S2 | Sprint Leader keeps the board current
Change Request CR-06 & CCB | R (reviews impact analysis) | A/R (PO in the CCB) | Sponsor decides
Rebaseline + configuration tags | R (tags) | A/R | baseline-v1.0, baseline-v1.1, v1.0
Test cases from AC | R (runs F2/F3, F4/F5, regression) | A/R (writes F1–F5 test cases; manual F1 run) | ≥ 1 test case per AC
UAT script & acceptance record | C | A/R | Run at Review 3 (13/11)
Hosting & Release v1.0 | A/R (Supabase + Vercel) | C | Tag v1.0 + release notes
EVM & Final Report | R (PMP / Workbook Final) | A/R (Final Report, EVM) | Hours from Jira Completed Work
Slides & demo video | R | A/R | Everyone presents
Member evaluation c0_Eval | Sprint 1, Sprint 3 | Sprint 2 | Sprint Leader evaluates members
Development Story Points per person (main developer, sheet 3)
Member | Sprint 1 | Sprint 2 | Sprint 3 | Total SP
Hồ Du Tuấn Đạt
Nguyễn Minh Chính
Planned hours per person (sheet 2, 'Both' split 50/50) vs. capacity
Member | Sprint 1 | Sprint 2 | Sprint 3 | Closure
Hồ Du Tuấn Đạt
Nguyễn Minh Chính
Capacity per person (h)

## 6_Deliverables
SUBMISSION SCHEDULE & FILE NAMES
Prefix HK261_SPM_FP_Team6_ · upload files individually, no zip · Excel files are cumulative · late: −10 % of the Sprint score per 5 h [03 §4.2, §7]
Submission | Due | Submitted by | File name | Content | Submitted?
eLearning item | 26/10 19:35 (late) | Nguyễn Minh Chính | HK261_SPM_FP_Team6_MasterPlan.xlsx | FinalProject: Master Plan and Timeline – this workbook | No
Sprint 1 | 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c1_ProjectPlan.docx | PMP v1.0 (7 parts) | No
Sprint 1 | 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c2_SprintBacklog_S1.xlsx | Product Backlog, Planning Poker log, Release Plan, Sprint Backlog S1, Burndown, Risk Register, Config Items | No
Sprint 1 | 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c3_SprintReport_S1.docx | Sprint Planning, Daily log, F1 test cases, Review, Retro, Status | No
Sprint 1 | 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c0_Eval_S1.xlsx | Leader evaluates members | No
Sprint 2 | 23:59 Thu 05/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c2_SprintBacklog_S2.xlsx | Updated workbook (Change Log, Risk, Issue Log, S2) | No
Sprint 2 | 23:59 Thu 05/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c3_SprintReport_S2.docx | Sprint 2 report + F2, F3 test cases + Weekly Status | No
Sprint 2 | 23:59 Thu 05/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c4_ChangeRequest_CR01.docx | CR form, impact analysis, CCB decision (CR01 vs CR06 file name: ask the lecturer) | No
Sprint 2 | 23:59 Thu 05/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c0_Eval_S2.xlsx | Leader evaluates members | No
Sprint 3 | 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c2_SprintBacklog_S3.xlsx | Updated workbook (S3, draft EVM) | No
Sprint 3 | 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c3_SprintReport_S3.docx | Sprint 3 report + F4, F5 test cases + release notes | No
Sprint 3 | 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c5_UAT.docx | UAT scripts and acceptance record | No
Sprint 3 | 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c0_Eval_S3.xlsx | Leader evaluates members | No
Final | 23:59 Sun 15/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c1_ProjectPlan_Final.docx | PMP updated after lecturer feedback and the CR | No
Final | 23:59 Sun 15/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c2_SprintBacklog_Final.xlsx | Complete workbook incl. EVM sheet | No
Final | 23:59 Sun 15/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c6_FinalReport.docx | Final Report + Lessons Learned + hosted URL + repo/board/video links | No
Final | 23:59 Sun 15/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c6_Slides.pptx | Final presentation slides | No
Final | 23:59 Sun 15/11 | Each member | Eval360_Team6_<StudentID>.xlsx | One 360° evaluation file per member | No
Final presentation: 07:00 Tuesday 17/11/2026 – 10 min + 5 min Q&A; every member presents [03 §8].

## 7_Timeline
TIMELINE 23/10 – 17/11/2026
Bars come from the planned dates in sheet 2. Navy = Sprint/phase · grey = work package · black = milestone · today's column is outlined in red.
WBS | Item | Start | Finish | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17
L1
L2
L2
L2
MS
L1
L2
L2
L2
L2
MS
L1
L2
L2
L2
MS
L1
L2
L2
MS

## 8_PlanningPoker
PLANNING POKER LOG – Release 1.0 (lecturer template BM01)
Estimation record 30/10/2026: NO voting rounds were held. Final SP = PO (Nguyễn Minh Chính) estimates from AI-suggested values, sized against reference stories 2 SP (hide book) / 3 SP (book detail) / 5 SP (search & filter). Round columns are empty on purpose. Đạt to confirm; a later real session replaces these values.
Session date/time | 30/10/2026 | [5 empty] | # | Member | Role
Channel / place | No session held – PO estimate (see A2) | [5 empty] | 1 | Hồ Du Tuấn Đạt | Developer · Sprint Leader S1, S3
Facilitator | Nguyễn Minh Chính (PO reads each story and its AC) | [5 empty] | 2 | Nguyễn Minh Chính | Product Owner + Developer · Sprint Leader S2
US ID | Item | Round 1 (cards: Đạt, Chính) | Round 2 | Round 3 | Final SP | Reasoning that led to agreement / notes
US-01 | Visitor registers with name, email and password (signs in as Customer) | – | – | – | 3 | One form; duplicate-email check; client + server validation. Same size as reference 3 (book detail)
US-02 | Registered user logs in and logs out | – | – | – | 3 | Session handling + locked-account and generic-error cases; similar to US-01
US-03 | Administrator creates accounts with a role and locks/unlocks accounts | – | – | – | 5 | List, create, lock/unlock, cannot lock self, session ends on lock; as large as reference 5 (search & filter)
US-04 | Admin functions blocked on the server for anyone who is not an administrator | – | – | – | 3 | One shared server guard, but a 403 check is needed on every /admin route
NFR-01 | Passwords stored as hashes; every form validated on client and server | – | – | – | 2 | bcrypt library + max-length rules; size of reference 2 (hide book)
NFR-03 | Site hosted on a free public URL until 17/11/2026 | – | – | – | 2 | Vercel + Supabase set-up and keep-alive; size of reference 2
US-05 | Administrator adds a book (title, author, category, price > 0, description, cover, stock) | – | – | – | 5 | Most fields of any form + cover upload (JPG/PNG ≤ 2 MB) + boundary checks; reference 5
US-06 | Administrator edits a book | – | – | – | 3 | Reuses the add form; adds not-found and no-change cases
US-07 | Administrator deletes (hides) a book without losing its record | – | – | – | 2 | Reference story (2 SP)
US-08 | Administrator manages categories | – | – | – | 3 | Add/rename/remove + unique name + 'in use by N books' rule
US-09 | Administrator manages authors | – | – | – | 3 | Same pattern as US-08
NFR-02 | At least 30 sample books loaded | – | – | – | 2 | Seed script that is safe to run twice
US-10 | Customer browses a grid of 12 books per page, newest first | – | – | – | 3 | Grid + pagination edge cases (page 0, too large, empty)
NFR-04 | Every page works on phone, tablet and desktop | – | – | – | 3 | Three breakpoints checked on every page + 44 px tap targets
US-11 | Customer opens a book's detail page and goes back to the same list page | – | – | – | 3 | Reference story (3 SP); Back keeps page/search/filter
US-12 | Customer searches by title or author | – | – | – | 3 | One case-insensitive query on title or author; special characters as text
US-13 | Customer filters by category and price range with search and pagination | – | – | – | 5 | Category + price range + search kept in the URL across pages; reference 5
NFR-05 | Book list loads in under 2 seconds | – | – | – | 2 | Measure 3 runs on the hosted site; add an index only if needed
US-24 | CR-06: Store Staff adds/edits books, manages categories and authors; cannot delete books or manage accounts | – | – | – | 5 | New role touches every admin route and screen; server-side checks; as large as US-03
US-25 | CR-06: each book shows 'Last updated by … at …' | – | – | – | 2 | Two audit columns + one display line
Questions the team asked the Product Owner (record at least 3) – proposed below; keep only those really asked and write the PO's answer
# | Question | PO answer
1 | US-05: is ISBN required for a book in Release 1.0 (F2 lists title, author, category, price, description, cover, stock)?
2 | NFR-05: is the < 2 s list load measured on a warm server, or must it also hold after a free-hosting cold start?
3 | US-08 / US-09: can a category or author that is still used by books be removed, or only hidden?
4 | US-24 (CR-06): may Store Staff delete categories and authors, or only add and edit them?