# Project Management Plan v1.0 – Team 6 Page Turners

Table of Contents

# PMP Part 1 – Project Charter

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0 | – | – | Lab 1 (SMART, stakeholders) and Lab 2 (Charter) were not submitted; no prior version exists [05 #21–22] |
| 1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Charter written new for Release 1.0 from the Final Project brief [03 §2] and TA baseline [04]. Objectives and stakeholders to be confirmed by the team |

## 1.1 Project identification

| Item | Value |
| --- | --- |
| Project | E-Commercial Book Store – Release 1.0 "Book Catalogue" |
| Customer / Sponsor | Ms. Le, owner of a multi-store book company (role played by Dr. Bùi Minh Phụng) |
| Performing team | Team 6 "Page Turners" – Hồ Du Tuấn Đạt, Nguyễn Minh Chính |
| Course | Software Project Management (72ITSE41503), class 261_72ITSE41503_01, Van Lang University |
| Duration | 23/10/2026 – 17/11/2026, 3 one-week Sprints + closure |
| Budget (BAC) | Planned person-hours × 200,000 VND – TBD (scenario 24,000,000 VND, see PMP-3 §3.6) |

## 1.2 Business case

Ms. Le's company sells through physical stores only. She wants an online bookshop with its own style that works on desktop, phone and tablet [03 §2]. Release 1.0 delivers the catalogue foundation (accounts, book management, browsing, details, search) on which ordering features can be added later.

## 1.3 SMART objectives

| # | Objective | Measure | Deadline |
| --- | --- | --- | --- |
| O1 | Deliver F1–F5 on a free public host | 100 % of Release 1.0 ACs pass in UAT | 13/11/2026 |
| O2 | Meet the NFRs | ≥ 30 sample books; list page < 2 s (median of 3); passwords hashed; client + server validation; responsive at 360/768/1280 px | 12/11/2026 |
| O3 | Control schedule and cost | SPI and CPI ≥ 0.9 at the end of S3 (AgileEVM) | 12/11/2026 |
| O4 | Control change | Every CR goes through the 5-step process with a CCB decision recorded within 1 working day of the CCB meeting | per CR |
| O5 | Run a transparent process | Board updated daily, Daily log every working day, every task has Original Estimate and Completed Work | each Sprint |

## 1.4 Scope

In scope (Release 1.0): F1 accounts & roles (register, login, logout, admin creates/locks accounts, ≥ 2 roles, server-side guard); F2 books, categories, authors (soft delete, price > 0, validation); F3 grid 12/page newest first, responsive; F4 detail with friendly not-found and Back-to-same-page; F5 search by title/author, filter by category and price range with pagination; NFRs; hosting until 17/11/2026 [03 §2.2]. CR-06 (Store Staff role) is added only if approved at CCB on 30/10.

Out of scope: shopping cart, payment, social login [03 §2.2]; orders, promotions, multi-store inventory, reviews, wishlist, recommendations (Release 2, see backlog section C).

## 1.5 Milestones

See PMP-3 §3.2 (M0 23/10 … M11 17/11).

## 1.6 Stakeholders

| Stakeholder | Role | Interest / influence | Key needs |
| --- | --- | --- | --- |
| Ms. Le (Dr. Bùi Minh Phụng) | Sponsor, Customer, CCB chair, UAT signer | High / High | Working increments, controlled change, honest data |
| Store staff of Ms. Le's company | Future users (CR-06) | High / Low | Update catalogue daily without full admin rights |
| Online customers | End users | High / Low | Find books fast on any device |
| Nguyễn Minh Chính | Product Owner + Developer, Leader S2 (to confirm) | High / High | Clear priorities, accepted items |
| Hồ Du Tuấn Đạt | Developer, Leader S1 & S3 (to confirm) | High / High | Realistic plan, stable hosting |
| Faculty of IT, VLU | Academic oversight | Low / Medium | Academic integrity |

## 1.7 Constraints

- Team of 2 must deliver all of F1–F5; features are not cut, workload is managed through capacity and the Release Plan [03 §2.2].

- Fixed dates: submissions every Thursday 23:59; late penalty −10 % per 5 h [03 §4.2].

- Free hosting only; site online until 17/11/2026.

- Rate 200,000 VND per person-hour; N = 3 Sprints.

## 1.8 Assumptions

- Each member can contribute the capacity recorded in plan/INPUTS.md §2 (TBD).

- Jira Free supports Original Estimate and Time Spent for the team-managed project (to verify [05 #18]).

- The free host and database tiers stay available until 17/11/2026.

- The Sponsor's CCB decision on CR-06 is given on 30/10/2026.

## 1.9 Success criteria

- UAT minutes signed with every Release 1.0 AC passed (and CR-06 ACs if approved).

- Tag v1.0 and release notes on the repository; site reachable by the lecturer.

- All submissions on time with consistent SP, hours and EVM figures across Workbook, Sprint Reports, Final Report and slides.

## 1.10 Approval

| Name | Role | Decision | Date |
| --- | --- | --- | --- |
| Dr. Bùi Minh Phụng | Sponsor | TBD | TBD |
| Nguyễn Minh Chính | Product Owner | TBD | TBD |
| Hồ Du Tuấn Đạt | Sprint Leader S1 | TBD | TBD |

# PMP Part 2 – Tailored Scrum Process

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 (TA) | 02/10/2026 | Team 6 | Scrum for the Team Assignment: one 2-week Sprint, 4 h/member/day, Slack #decisions, Jira board [TA Process.docx] |
| 1.0-FP-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Adapted to the Final Project: 1-week Sprints Fri→Thu (N = 3), leader rotation S1/S3 vs S2 = PO, time tracking per task, CR/CCB step, Git PR review [03 §4–§5] |

## 2.1 Roles and people

| Role | Person | Responsibilities |
| --- | --- | --- |
| Sponsor / Customer | Dr. Bùi Minh Phụng (Ms. Le) | Approves PMP v1.0, issues CRs, chairs CCB, attends Reviews, signs UAT |
| Product Owner (fixed) + Developer | Nguyễn Minh Chính (to confirm) | Orders backlog, writes/clarifies ACs, accepts items as Done, represents team at CCB |
| Sprint Leader / Scrum Master | S1 Hồ Du Tuấn Đạt · S2 Nguyễn Minh Chính · S3 Hồ Du Tuấn Đạt (to confirm) | Runs Planning, Daily, Retro; keeps board current; submits Sprint files; presents Review |
| Developers | Both | Split tasks, estimate hours, build, test, log actual hours |

## 2.2 Events and timeboxes

| Event | When | Timebox | Output |
| --- | --- | --- | --- |
| Sprint Planning | Friday after Review (S1: 28/10 catch-up) | ≤ 45 min | Sprint Goal, capacity, items, tasks ≤ 1 person-day in Excel Sx_Backlog, then Jira |
| Daily Scrum | Every working day, asynchronous allowed (channel TBD: Zalo/Teams/Slack) | ≤ 10 min | Daily log (yesterday / today / blockers / hours logged) |
| Backlog refinement | Mid-Sprint (Tuesday) | 30 min | Next items meet DoR; Planning Poker for new/changed items |
| Sprint Review | Friday in class | with Retro 30 min + ~10 min presentation | Demo against ACs, burndown, plan vs actual hours |
| Sprint Retrospective | Friday in class after Review | (incl. above) | ≥ 2 action items tracked in the next Sprint |
| CCB meeting | When a CR is issued (CR-06: 30/10) | 15 min | Approve / Reject / Defer with reason |

## 2.3 Artifacts

Product Backlog (pm/backlog/product-backlog.md → Workbook sheet), Sprint Backlog per Sprint, Increment on the hosted URL, burndown (Jira + Workbook), Daily log, Risk Register, Issue Log, Change Log, Config Items, EVM sheet; DoR and 3-level DoD (PMP-4).

## 2.4 Tools

| Purpose | Tool |
| --- | --- |
| Board, estimates, actual hours | Jira Software Cloud (Free, team-managed, key BOOK) – lecturer invited as Reader (TBD) |
| Planning workbook | Excel HK261_SPM_FP_Team6_c2_SprintBacklog_Sx.xlsx (cumulative) |
| Source & configuration | GitHub repo Tdat10052499/E-Commercial-Book-Store, PR review |
| Hosting | Free tier (decided at P04) |
| Communication | Daily channel TBD; email to Sponsor; class meetings |

## 2.5 Tailoring decisions and related risks

| Decision | Reason | Risk introduced | Mitigation |
| --- | --- | --- | --- |
| 1-week Sprints, Fri→Thu | Fixed by the brief | Little buffer per Sprint | Small tasks (≤ 1 person-day), daily re-plan |
| Asynchronous Daily Scrum allowed | 2 members, different schedules | Blockers noticed late | Log template; 24 h response rule (PMP-7) |
| PO is also a Developer and Leader S2 | Team of 2 [03 §4.1] | Conflict between accepting and building | Story-DoD checked by the other member |
| Excel first, then Jira | Required by the brief [03 §4.2] | Data inconsistency | Leader reconciles Excel and Jira each Planning |
| Code review by the only other member | 2 members | Review delays block merges | Review within 12 h; small PRs |
| AI assistance for drafting | Allowed with declaration [03 §4.2] | Content not understood by members | Every AI-assisted change logged in pm/ai-usage-log.md and reviewed in PR |

# PMP Part 3 – Master Plan & Release Plan

Project: E-Commercial Book Store – Release 1.0 (Book Catalogue, F1–F5) Team: Team 6 "Page Turners" · Sponsor/Customer: Dr. Bùi Minh Phụng (as Ms. Le) Period: Fri 23/10/2026 – Tue 17/11/2026 (GMT+7)

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0.1 (TA) | 15/10/2026 | Team 6 | Team Assignment release planning: velocity assumed 22 SP per 2-week Sprint; Must + Should = 79 SP over ~4 Sprints [04 §4] |
| 1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Rebaselined to the Final Project brief: 3 one-week Sprints, scope F1–F5 only, cart/payment/social login out of scope [03 §2.2, §5]; capacity-based velocity; BAC formula at 200,000 VND/h; CR-06 recorded as pending CCB |
| 1.1-draft | 30/10/2026 | Nguyễn Minh Chính (PO, AI-assisted) | Roles confirmed; capacity 20 h per member per Sprint adopted as plan value (40 h/Sprint, 120 h, BAC 24.0 M VND); CR-06 Option B recommended; Excel version added |

Status of figures. Every number marked (plan) is a planning value. Values marked TBD need human input (capacity, Planning Poker votes, Jira actuals) and are tracked in plan/INPUTS.md. No actual figure appears in this document.

## 3.1 Release goal

Deliver a hosted, responsive Book Catalogue website in which administrators manage accounts, roles and books, and customers browse, view, search and filter at least 30 sample books, accepted by the Sponsor through UAT on 13/11/2026 [03 §2, §6.3].

## 3.2 Milestones (fixed by the brief)

| # | Milestone | Date / time (GMT+7) | Evidence | Source |
| --- | --- | --- | --- | --- |
| M0 | Project start, brief issued | Fri 23/10 | – | [03 §5] |
| M1 | CR-06 issued by Sponsor | Tue 27/10 | CR-06 in Change Log | [CR-06] |
| M2 | Sprint 1 submission (c1, c2, c3, c0) | Thu 29/10 23:59 | eLearning upload | [03 §7] |
| M3 | Review/Retro 1 + CCB for CR-06 | Fri 30/10 | Review slides, CCB decision | [03 §5], [CR-06 §5] |
| M4 | Baseline v1.0 tagged (baseline-v1.0) | Fri 30/10 | Git tag | PMP-6 |
| M5 | Sprint 2 submission (c2, c3, c4 CR, c0) | Thu 05/11 23:59 | eLearning upload | [03 §7] |
| M6 | Review/Retro 2 | Fri 06/11 | Review slides | [03 §5] |
| M7 | Release v1.0 tagged + release notes | Thu 12/11 | Git tag, notes | [03 §6.3] |
| M8 | Sprint 3 submission (c2, c3, c5 UAT, c0) | Thu 12/11 23:59 | eLearning upload | [03 §7] |
| M9 | Review 3 + UAT with customer | Fri 13/11 | Signed UAT minutes | [03 §6.3] |
| M10 | Final submission (c1 Final, c2 Final, c6 Report, c6 Slides, Eval360) | Sun 15/11 23:59 | eLearning upload | [03 §7] |
| M11 | Final presentation; site online until end of day | Tue 17/11 07:00 | Live demo | [03 §8] |

## 3.3 Sprint plan and leader rotation

Sprints run Friday → Thursday, one week each, N = 3 [03 §5]. Rotation for a 2-person team: the PO leads S2, the other member leads S1 and S3 [03 §4.1].

| Sprint | Dates | Leader | Sprint Goal (plan) | Increment | PM focus (rubric S4) |
| --- | --- | --- | --- | --- | --- |
| S1 – Plan baseline & F1 | 23/10 – 29/10 | Hồ Du Tuấn Đạt | "Users can register, log in and log out; an administrator can create and lock accounts; non-admins are blocked from admin functions on the server." | F1 | PMP v1.0 |
| S2 – Execution, monitoring & change | 30/10 – 05/11 | Nguyễn Minh Chính (PO) | "Admins manage books, categories and authors (soft delete), and customers browse 12 books per page, newest first, on any device." (+ CR-06 if approved) | F2, F3 (+CR-06) | CR + risk/issue |
| S3 – Complete & acceptance | 06/11 – 12/11 | Hồ Du Tuấn Đạt | "Customers open book details and search/filter by title, author, category and price range together with pagination; Release v1.0 passes UAT." | F4, F5 | UAT + Release |
| Closure | 13/11 – 17/11 | Both | Final Report, EVM, Lessons Learned, slides, video | Release 1.0 online | – |

Feature allocation follows the brief's reference Sprints [03 §2.2]. Any change is decided at Sprint Planning and recorded in §3.8.

## 3.4 Allocation of backlog items to Sprints (plan)

SP come from the Planning Poker log (pm/backlog/planning-poker-log.md). Until votes are recorded, SP are TBD.

| Sprint | Items | SP (plan) |
| --- | --- | --- |
| S1 | US-01 Register · US-02 Log in/out · US-03 Admin creates & locks accounts · US-04 Server-side role guard · NFR-01 Password hashing & validation · NFR-03 Hosting/deploy skeleton | TBD |
| S2 | US-05 Add book · US-06 Edit book · US-07 Hide (soft delete) book · US-08 Manage categories · US-09 Manage authors · NFR-02 Seed ≥30 books · US-10 Book grid 12/page newest first · NFR-04 Responsive UI | TBD |
| S2 (if CR-06 approved, option per CCB) | US-24 Store Staff role & permissions · US-25 "Last updated by" audit | TBD |
| S3 | US-11 Book detail page (+friendly not-found, Back keeps page) · US-12 Search by title/author · US-13 Filter by category & price range with pagination · NFR-05 List page < 2 s | TBD |
| Release 1.0 total |  | PSP = TBD |

## 3.5 Capacity and expected velocity

Formula (per Sprint): Capacity (h) = Σ members (available days × focus hours/day). Expected velocity is derived from capacity, not copied from the TA (22 SP / 2 weeks is not applicable to 1-week Sprints [05 #10]).

| Sprint | Đạt (h) | Chính (h) | Capacity (h) | Source |
| --- | --- | --- | --- | --- |
| S1 | 20 | 20 | 40 | plan/INPUTS.md §2 (plan value, PO 30/10/2026) |
| S2 | 20 | 20 | 40 |  |
| S3 | 20 | 20 | 40 |  |
| Release | 60 | 60 | 120 |  |

Planning scenario – adopted by the PO on 30/10/2026 as the plan value (Đạt to confirm). The TA working agreement used 4 focus hours per member per day [TA Process §a.3]. With 5 working days per Sprint (Fri, Mon–Thu) this gives 4 × 5 × 2 = 40 h per Sprint (plan), 120 h for the release. The team must confirm or replace this figure.

Expected velocity (SP per Sprint) = PSP ÷ 3 when the planned work is spread evenly, checked against the hours that the Sprint's tasks require (Σ task estimates ≤ capacity). It is recalculated from actual velocity at Planning 2 and 3 [03 §6.2].

## 3.6 Budget (BAC) and EVM baseline

- BAC = total planned person-hours of the release × 200,000 VND [03 §6.4].

- Plan: 120 h × 200,000 = 24,000,000 VND (plan; capacity confirmed by the PO 30/10/2026). The Excel version of this plan is pm/plan/HK261_SPM_FP_Team6_MasterPlan.xlsx (same figures).

- Baseline per Sprint: PV(n) = BAC × n / 3 → 8.0 M (S1), 16.0 M (S2), 24.0 M (S3) under the scenario.

- EV = BAC × (cumulative SP meeting DoD ÷ PSP); AC = actual cumulative hours from Jira Completed Work × 200,000. SV, CV, SPI, CPI, EAC, ETC follow [03 §6.4]. Actuals are collected per Sprint into plan/INPUTS.md §4.

- If CR-06 is approved, PSP and BAC are rebaselined; both baseline and rebaseline are kept (§3.8).

## 3.7 Master schedule (work packages by date)

Internal windows are the team's proposal and may be adjusted at Sprint Planning. Phase IDs refer to plan/ROADMAP.md.

| Phase | Work package | Start | Due | Owner | Depends on |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 (23–29/10) |  |  |  |  |  |
| P00 | Repo, branches, access (GV invited) | 27/10 | 27/10 | Đạt | – |
| P01 | Kick-off, roles, working agreement, capacity | 27/10 | 28/10 | Both | P00 |
| P02 | Product Backlog v1.0 (GWT, DoR) | 27/10 | 28/10 | PO | P01 |
| P03 | Planning Poker, Release Plan, BAC | 28/10 | 28/10 | PO + Leader | P02 |
| P04 | Stack, scaffold, deploy skeleton | 27/10 | 28/10 | Đạt | P01 |
| P05 | Sprint Planning 1 → Jira | 28/10 | 28/10 | Leader | P03 |
| P06–P07 | Build F1; F1 test cases | 28/10 | 29/10 | Both | P04, P05 |
| P08 | PMP v1.0 (7 parts) | 27/10 | 29/10 | Leader + PO | P01, P03 |
| P09 | CR-06 Change Log, impact analysis, options | 28/10 | 29/10 | PO | P03 |
| P10 | Daily log, burndown, actual hours | 23/10 | 29/10 | Leader | continuous |
| P11 | Package & submit S1 | 29/10 | 29/10 23:59 | Leader | above |
| P12 | Review/Retro 1 + CCB | 30/10 | 30/10 | Leader + PO | P11 |
| Sprint 2 (30/10–05/11) |  |  |  |  |  |
| P13 | Sprint Planning 2 (actual velocity S1) | 30/10 | 30/10 | Leader | P12 |
| P14 | Update baseline per CCB, tag | 30/10 | 31/10 | PO | CCB decision |
| P15 | Build F2 (+ seed ≥30 books) | 31/10 | 03/11 | Both | P13 |
| P16 | Build F3 | 02/11 | 04/11 | Both | P15 |
| P17 | Build CR-06 (if approved) | 01/11 | 04/11 | Both | P14 |
| P18 | Test cases F2, F3, CR-06 + regression F1 | 03/11 | 05/11 | Both | P15–P17 |
| P19 | Weekly Status, risk & issue log | 30/10 | 05/11 | Leader | continuous |
| P20 | c4 Change Request form | 31/10 | 05/11 | PO | P14 |
| P21 | Package & submit S2 | 05/11 | 05/11 23:59 | Leader | above |
| P22 | Review/Retro 2 | 06/11 | 06/11 | Leader | P21 |
| Sprint 3 (06–12/11) |  |  |  |  |  |
| P23 | Sprint Planning 3 (actual velocity S2) | 06/11 | 06/11 | Leader | P22 |
| P24–P25 | Build F4, F5 | 07/11 | 10/11 | Both | P23 |
| P26 | Tests F4, F5, regression F1–F3, performance | 10/11 | 11/11 | Both | P24, P25 |
| P27 | Release v1.0: merge to main, tag, notes | 11/11 | 12/11 | Leader | P26 |
| P28 | UAT script (all ACs) | 10/11 | 12/11 | PO | P26 |
| P29 | Monitoring + draft EVM | 06/11 | 12/11 | Leader | continuous |
| P30 | Package & submit S3 | 12/11 | 12/11 23:59 | Leader | above |
| P31 | Review 3 + UAT + minutes | 13/11 | 13/11 | Leader + PO | P30 |
| Closure (13–17/11) |  |  |  |  |  |
| P32 | Final hosting, demo accounts, closure data | 13/11 | 14/11 | Đạt | P31 |
| P33 | Final Report, EVM, Lessons Learned, PMP/Workbook Final | 13/11 | 15/11 | Both | P31, P32 |
| P34 | Slides + demo video ≤ 3 min | 14/11 | 15/11 | Both | P33 |
| P35 | Final submission + Eval360 each | 15/11 | 15/11 23:59 | Both | P33, P34 |
| P36 | Final presentation | 16/11 | 17/11 07:00 | Both | P35 |

Critical path: P02 → P03 → P05 → P06 → P11 → P13 → P15 → P16 → P18 → P21 → P23 → P25 → P26 → P27 → P31 → P33 → P35. Event gates that cannot be moved: CCB (30/10), Reviews (30/10, 06/11, 13/11), UAT (13/11).

## 3.8 Baseline and change history of this plan

| Baseline | Date | Trigger | PSP | BAC | Tag |
| --- | --- | --- | --- | --- | --- |
| Baseline v1.0 | 30/10/2026 | Sprint 1 submission | TBD | TBD | baseline-v1.0 |
| Rebaseline v1.1 | TBD | CCB decision on CR-06 (if Approve) | TBD | TBD | baseline-v1.1 |

### Schedule variance observed (as of 30/10/2026 00:45)

- Sprint 1 artefacts were not yet in the repository at the 29/10 23:59 deadline. If the eLearning upload is also late, the penalty is −10 % of the Sprint score per 5 hours [03 §4.2]. Submission time: TBD (Leader to record). Logged as issue I-01 and as an input for Retro 1.

# PMP Part 4 – Quality Plan

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0 (TA) | 15/10/2026 | Team 6 | Single-level DoD, 7 items (DoD-1…DoD-7) [04 §2] |
| 1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Split into 3-level DoD (Story / Sprint / Release) with evidence and checker [05 #12]; DoD-2 changed from "merged to main" to "merged to develop via reviewed PR" [05 #13]; added metrics and test approach |

## 4.1 Definition of Done – 3 levels

### Story DoD (each backlog item)

| # | Criterion | Evidence | Checker |
| --- | --- | --- | --- |
| SD-1 | Every AC of the item passes (from v0 DoD-1) | Test case file with actual result = Pass | PO |
| SD-2 | Code reviewed by the other member and merged into develop through a PR (v0 DoD-2, revised) | Approved PR link | Reviewer |
| SD-3 | Automated tests for new logic pass (v0 DoD-3) | Test run output / CI | Developer |
| SD-4 | Works at 360/768/1280 px on Chrome and one other browser (v0 DoD-4) | Screenshots | Reviewer |
| SD-5 | Client and server validation present; no secret in code | PR checklist | Reviewer |
| SD-6 | Jira task Done with Completed Work logged (v0 DoD-7) | Jira | Leader |

### Sprint DoD (end of each Sprint)

| # | Criterion | Evidence | Checker |
| --- | --- | --- | --- |
| SpD-1 | All committed items meet Story DoD; unfinished items returned to the Product Backlog | Sprint Backlog status | PO |
| SpD-2 | No open high-severity defect (v0 DoD-5) | Defect list | Leader |
| SpD-3 | Increment deployed on the hosted URL and demonstrated against ACs | URL + Review demo | Sponsor |
| SpD-4 | Regression of earlier features passes | Regression test results | Developer |
| SpD-5 | Workbook, Sprint Report and Jira figures reconciled; files submitted on time | Submission receipt | Leader |

### Release DoD (Release 1.0)

| # | Criterion | Evidence | Checker |
| --- | --- | --- | --- |
| RD-1 | F1–F5 (+ approved CRs) all ACs pass in UAT | Signed UAT minutes | Sponsor |
| RD-2 | NFRs met: ≥ 30 books, list < 2 s, hashing, validation, responsive | NFR test records | PO |
| RD-3 | develop merged into main, tag v1.0, release notes | GitHub release | Leader S3 |
| RD-4 | Docs updated: README (how to run), release notes, user notes (v0 DoD-6) | Repo | Reviewer |
| RD-5 | Site online until 17/11/2026 with demo accounts | URL check | Leader S3 |

## 4.2 Quality metrics

| Metric | Formula | Target | Collected |
| --- | --- | --- | --- |
| AC pass rate | ACs passed ÷ ACs tested | 100 % at Sprint end | Each Sprint, test case file |
| Test case coverage | ACs with ≥ 1 test case ÷ total ACs | 100 % | Each Sprint |
| Defects by severity | Count of Critical / High / Medium / Low | 0 open Critical/High at Sprint end | Defect list |
| Reopen rate | Items reopened after Done ÷ items Done | ≤ 10 % | Each Sprint |
| Page load | Median of 3 loads of list page | < 2 s | S2, S3 |

## 4.3 Test approach

- Test cases from ACs: at least one test case per AC, format GWT → steps → expected → actual → Pass/Fail [03 §6.1-7].

- Levels: automated tests for validation, auth and permission logic; manual functional tests per AC; regression of earlier features each Sprint; performance check of the list page; UAT script mapped to every AC in S3.

- Defect severity: Critical (blocks a Must AC or security), High (AC fails, workaround exists), Medium (non-AC behaviour), Low (cosmetic).

# PMP Part 5 – Risk Management Plan

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | New; inputs from gap analysis [05 §5]. P and I scores are proposals to be confirmed by the team |

## 5.1 Process

- Identify at Planning, Daily (blockers) and Retro; anyone may add a risk.

- Assess probability P (1–5) and impact I (1–5); score = P × I. 1–6 Low, 8–12 Medium, 15–25 High.

- Plan response: Avoid, Mitigate, Transfer, Accept; each risk has an owner and a trigger.

- Monitor every Sprint (status Open / Watching / Occurred / Closed). When a risk occurs it moves to the Issue Log with the action taken [03 §6.2-5].

- Report the top risks in each Sprint Review and Weekly Status Report.

## 5.2 Risk register v1.0 (status at 30/10/2026)

| ID | Risk (cause → event → effect) | Cat. | P | I | P×I | Strategy & response | Owner | Trigger | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Only 2 members must deliver F1–F5 plus heavy PM documentation → workload exceeds capacity → items slip | Resource | 4 | 4 | 16 | Mitigate: tasks ≤ 1 person-day, capacity-based plan, AI-assisted drafting with review | Leader | Burndown flat for 2 days | Occurred → I-01 |
| R02 | Lab 1/Lab 2/TA week 2 not submitted → PMP must be written from scratch → S1 late | Schedule | 5 | 3 | 15 | Mitigate: reuse TA files, draft PMP early | Leader S1 | PMP not ready 24 h before deadline | Occurred → I-01 |
| R03 | Free host sleeps (cold start) → list page > 2 s or lecturer cannot open site | Technical | 3 | 4 | 12 | Mitigate: pick host without long sleep or add keep-alive ping; measure warm & cold | Đạt | First load > 5 s | Open |
| R04 | Jira Free lacks time tracking fields → no actual hours → EVM AC invalid | Tool | 2 | 5 | 10 | Mitigate: verify in S1; fallback: hours sheet in Workbook | Leader | Fields missing on issue | Open |
| R05 | CR-06 approved → extra scope and F1 rework → S2 overloaded | Scope | 4 | 3 | 12 | Mitigate: ≥ 2 options at CCB incl. phased delivery; rebaseline PSP/BAC | PO | CCB Approve | Open |
| R06 | Planning Poker evidence or regular commits missing → B4, S5 and individual factor reduced | Quality/Process | 3 | 4 | 12 | Avoid: photo of each reveal; commit at least daily per member | Both | No commit by a member in 2 days | Open |
| R07 | eLearning dates differ from the brief → wrong item or time used for upload | Schedule | 3 | 3 | 9 | Mitigate: ask lecturer; submit by brief date | Leader | Upload slot not found | Open |
| R08 | Security defect (plain passwords, missing server-side role check) → AC/NFR fail at UAT | Quality | 2 | 5 | 10 | Avoid: bcrypt, server guards, permission tests | Đạt | Test fails | Open |
| R09 | A member is sick or busy with other exams → capacity drops | Resource | 3 | 3 | 9 | Mitigate: shared knowledge via PR reviews; buffer in S3 | Leader | Member reports unavailability | Open |
| R10 | Integration of F3/F4/F5 (pagination + search + Back) breaks state → F4/F5 ACs fail | Technical | 3 | 3 | 9 | Mitigate: keep page/filter in URL query from S2 | Chính | Back loses page in test | Open |

## 5.3 Issue Log (risks that occurred)

| ID | From risk | Date | Description | Impact | Action | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| I-01 | R01, R02 | 30/10/2026 | Sprint 1 artefacts not completed in the repository by 29/10 23:59 | Possible late penalty (−10 % / 5 h); less time for F1 | Catch-up night 29–30/10 with AI-assisted drafting; record submission time; discuss in Retro 1 | Leader S1 | Open |

# PMP Part 6 – Configuration Management Plan

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | New; branching per CLAUDE.md §5; CR/CCB process per [03 §6.2-3] |

## 6.1 Configuration items (CI)

| CI-ID | Item | Type | Location | Owner | Baseline |
| --- | --- | --- | --- | --- | --- |
| CI-01 | Project Management Plan (7 parts) | Document | pm/pmp/ → c1_ProjectPlan.docx | Leader | baseline-v1.0 |
| CI-02 | Project Workbook | Spreadsheet | deliverables/Sx/c2_SprintBacklog_Sx.xlsx | Leader | baseline-v1.0 |
| CI-03 | Product Backlog & DoR | Document | pm/backlog/ | PO | baseline-v1.0 |
| CI-04 | Release Plan & BAC | Document | pm/pmp/03-master-release-plan.md | PO + Leader | baseline-v1.0 |
| CI-05 | Sprint Reports | Document | pm/sprints/Sx/ → c3_SprintReport_Sx.docx | Leader | per Sprint |
| CI-06 | Change Log & CR forms | Document | pm/change/ → c4_ChangeRequest_CR01.docx | PO | per CR |
| CI-07 | Source code | Code | app/ | Developers | tag per release |
| CI-08 | Database schema & seed | Database | app/db/ | Đạt | tag per release |
| CI-09 | Test cases & UAT script | Document | pm/sprints/Sx/, pm/uat/ | Developers | per Sprint |
| CI-10 | Hosting configuration (no secrets) | Config | app/README.md, host dashboard | Đạt | v1.0 |

## 6.2 Naming and versioning

- Submitted files: HK261_SPM_FP_Team6_<code>_<Name>[_Sx].<ext> [03 §7]; Excel files are cumulative.

- Document versions: 0.x draft → 1.0 baseline → 1.x approved changes → Final. Every inherited document has a version history table.

- Software versions: semantic tags v0.1 (S1), v0.2 (S2), v0.3 (S3), v1.0 (release).

## 6.3 Branching strategy

- main: release only; receives merges from develop; tagged. No direct commits [03 §4.2].

- develop: integration branch; changes enter only through PRs reviewed by the other member.

- Working branches: feat/Pxx-<desc> (code), docs/Pxx-<desc> (PM documents), fix/<desc>.

- Branch protection on main and develop: PR required, 1 approval.

## 6.4 Commit convention

Conventional Commits: feat(F1): add login, docs(pmp): draft risk register, fix(F3): pagination off-by-one, chore(plan): mark P05 done, followed by Refs: Pxx. Each member commits regularly in every Sprint.

## 6.5 Baselines and tags

| Tag | When | Contents |
| --- | --- | --- |
| baseline-v1.0 | After S1 submission | PMP v1.0, Backlog v1.0, Release Plan baseline, F1 |
| baseline-v1.1 | After CCB approval of a CR | Updated backlog, Release Plan rebaseline, risk register |
| v1.0 | 12/11/2026 | Release 1.0 code + release notes |

## 6.6 Change control process (CR and CCB)

- Record: every request (from Sponsor or team) is logged in the Change Log with ID, date, requester, description, priority.

- Analyse impact: scope (items, ACs), schedule (Sprint), cost (hours × 200,000 VND), quality (regression), risk; SP by Planning Poker.

- CCB decision: CCB = PO + Sprint Leader + Sponsor. The team presents ≥ 2 options; the Sponsor decides Approve / Reject / Defer with a reason.

- Update baseline (if approved): Product Backlog, ACs, Release Plan (PSP, BAC – baseline kept, rebaseline added), risk register; tag baseline-v1.x.

- Communicate to stakeholders per PMP-7 within 24 h. No change enters a Sprint without a CCB decision; the team does not build CR scope before approval.

# PMP Part 7 – Communication Plan

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0 (TA) | 02/10/2026 | Team 6 | Communication plan in TA Assign.xlsx; Slack #decisions for feedback [TA Process.docx] |
| 1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Updated for Final Project roles, weekly Sprint events, CCB and Weekly Status Report. Channel names to be confirmed |

## 7.1 Communication matrix

| Stakeholder | Information | Channel | Frequency | Sender |
| --- | --- | --- | --- | --- |
| Sponsor (Dr. Phụng / Ms. Le) | Sprint files (c0–c3) | eLearning | Weekly, Thu 23:59 | Sprint Leader |
| Sponsor | Sprint Review demo, burndown, plan vs actual, risks | In class | Weekly, Friday | Sprint Leader |
| Sponsor | Change impact & options; CCB decision record | CCB meeting + Change Log + c4 form | Per CR | PO |
| Sponsor | Weekly Status Report (G/A/R scope, schedule, cost, quality) | eLearning / email | Weekly from S2 | Sprint Leader |
| Sponsor | Board and repo access | Jira (Reader), GitHub | Continuous | Đạt |
| Team | Daily Scrum log | Channel TBD (Zalo/Teams/Slack) | Every working day | Each member |
| Team | Decisions, feedback | #decisions thread / Daily log | When made | Whoever decides |
| Team | Code changes | GitHub PR | Per task | Author → reviewer |
| Team | Final Report, UAT minutes | eLearning | 13/11, 15/11 | Leader S3 |

## 7.2 Response rules

- Team messages: reply within 12 h on working days; blockers within 4 h.

- PR review: within 12 h.

- Sponsor questions: answered within 24 h by the PO (scope) or Leader (process).

- Escalation: blocker > 24 h → raised to Sponsor in the next class or by email.

## 7.3 Scrum event calendar

| Date | Event |
| --- | --- |
| Fri 23/10 | Brief issued; Sprint 1 starts |
| Tue 27/10 | CR-06 received |
| Thu 29/10 23:59 | S1 submission |
| Fri 30/10 | Review/Retro 1, CCB CR-06, Planning 2 |
| Thu 05/11 23:59 | S2 submission |
| Fri 06/11 | Review/Retro 2, Planning 3 |
| Thu 12/11 23:59 | S3 submission |
| Fri 13/11 | Review 3 + UAT |
| Sun 15/11 23:59 | Final submission |
| Tue 17/11 07:00 | Final presentation |
| Daily (working days) | Daily Scrum ≤ 10 min, time TBD |