## 1_Proposal_Approval
MASTER PLAN – E-COMMERCIAL BOOK STORE RELEASE 1.0 (Team 6 – Page Turners)
Proposal v0.4 – restructured into the class Master Plan layout (30/10) ¦ Prepared by Nguyễn Minh Chính (PO) with Hồ Du Tuấn Đạt ¦ Schedule 23/10 – 17/11/2026
Course | Software Project Management (72ITSE41503) – Final Project, Semester 261
Sponsor / Customer | Dr. Bùi Minh Phụng (lecturer) in the role of Ms. Le – approves the plan, issues the Change Request, signs UAT
Release 1.0 scope | F1 System administration · F2 Book management · F3 Book list · F4 Book details · F5 Search/filter [03 §2.2]
Out of scope | Shopping cart, payment, social login → 13 backlog items set to Won't (R1.0) (sheet 3)
Minimum non-functional | Responsive · ≥ 30 sample books · list page < 2 s · client + server validation · hashed passwords · free hosting online until 17/11
Tools | Jira (space ECBS: board, Original Estimate, Completed Work) · GitHub repo (main/develop, reviewed PRs, tags) · Excel workbook · proposed stack Next.js + PostgreSQL on free hosting (to confirm)
Effort & budget | Sprints 1–3: 152.5 h planned (WBS) → BAC = 30,500,000 VND · capacity 168 h · PSP: TBD
A. PROPOSED SPRINT LEADER ROTATION (Option A – recommended)
Sprint | Dates | Sprint Leader | Product Owner | Sprint PM focus | Increment | Why this Leader | Submission / Review
Sprint 1 | Fri 23/10 – Thu 29/10 | Hồ Du Tuấn Đạt | Nguyễn Minh Chính | PMP v1.0 (7 parts), Product Backlog v1.0, Planning Poker, Release Plan, BAC, Sprint Planning 1; record CR-06 | F1 – System administration + hosting | Scrum Master in Lab 3 and the TA; owns the repo and the Jira site, so he sets up the baseline and tooling | Due 23:59 Thu 29/10 · Review 1 + CCB: Fri 30/10
Sprint 2 | Fri 30/10 – Thu 05/11 | Nguyễn Minh Chính | Nguyễn Minh Chính | CR-06 in 5 steps + CCB, Weekly Status Report, risk register and issue log, F2/F3 test cases | F2 – Book management · F3 – Book list (+ CR-06 if approved) | 2-member rule: the PO leads Sprint 2 [03 §4.1]; the PO wrote the AC that the CR changes | Due 23:59 Thu 05/11 · Review 2: Fri 06/11
Sprint 3 | Fri 06/11 – Thu 12/11 | Hồ Du Tuấn Đạt | Nguyễn Minh Chính | Release v1.0 (tag + release notes), UAT script, EVM draft, F4/F5 test cases, regression F1–F3 | F4 – Book details · F5 – Search/filter | Second Sprint for the non-PO member [03 §4.1]; backend owner for search/filter and the release tag | Due 23:59 Thu 12/11 · Review 3 + UAT: Fri 13/11
Closure | Fri 13/11 – Tue 17/11 | Whole team | Nguyễn Minh Chính | Final Report (plan vs. actual, EVM), Lessons Learned, slides, demo video | Release 1.0 online until end of 17/11 | Not a Sprint – no Leader turn; Chính coordinates the Final Report | Final submission: 23:59 Sun 15/11 · Presentation: 07:00 Tue 17/11
B. OPTIONS COMPARED
Option | Sprint 1 | Sprint 2 | Sprint 3 | Pros | Cons / risks | Rating
A (recommended) | Hồ Du Tuấn Đạt | Nguyễn Minh Chính (PO) | Hồ Du Tuấn Đạt | Keeps the Lab 3 / TA roles (Chính PO, Đạt Scrum Master); Đạt, who owns the repo and Jira, leads the setup Sprint; the PO is the Leader when the CR is processed. | In Sprint 2 the PO and the Leader are the same person at the CCB → Đạt reviews the impact analysis before the CCB. | ★★
B | Nguyễn Minh Chính | Hồ Du Tuấn Đạt (PO) | Nguyễn Minh Chính | Chính leads twice and keeps the board, where he already did the TA Week 2 setup. | Changes the PO two weeks before the end; Đạt would have to take over the backlog and AC written by Chính; breaks continuity with Lab 3. | ★
With 2 members the rule allows only these two patterns: the PO leads Sprint 2, the other member leads Sprints 1 and 3 [03 §4.1].
C. DECISIONS FOR APPROVAL (choose in the 'Status' column – yellow cells)
# | Item | Proposal |  | Rationale |  | Status | Reviewer notes
1 | Leader rotation & PO | Option A: Đạt (S1) → Chính (S2) → Đạt (S3); PO = Chính, fixed, also a Developer. Fixed in PMP v1.0. |  | Mandatory 2-member rule [03 §4.1]; continuity with Lab 3 and the TA. |  | Pending
2 | Rebaseline Product Backlog | Backlog v0 (23 items, 99 SP) remapped to F1–F5: 14 Release 1.0 items (new: US-24 categories, US-25 authors, NFR-01, NFR-02); 13 items → Won't (R1.0); 29 items total (sheet 3). |  | Spec scope [03 §2.2]; ≥ 15 items kept; gap analysis [05 §1, §4]. |  | Pending
3 | Item allocation per Sprint | Reference plan: S1 F1 + hosting · S2 F2 + F3 + seed data / < 2 s check · S3 F4 + F5 + release. |  | Every Increment is shown on the hosted URL; the < 2 s check is done on the page it measures. |  | Pending
4 | Capacity & budget | Capacity 28 h/person/Sprint (PO assumption, Đạt to confirm). Effort from the WBS: 152.5 h → BAC = 30,500,000 VND. Sprint 1 is over capacity by 5.5 h. |  | BAC = planned person-hours × 200,000 VND [03 §6.4]; tasks ≤ 1 person-day with owner and hours [03 §6.1 item 5]. |  | Pending
5 | Estimation | SP only from Planning Poker with every round logged (sheet 8, BM01 format); expected velocity from capacity until the actual Sprint 1 velocity exists. |  | Planning Poker evidence is graded (B4) and was missing last year [03 §8]. |  | Pending
6 | Change Request CR-06 | Logged; impact analysis with options A (all in S2) / B (S2 + S3) / C (defer) for the CCB on 30/10; enters the plan only if approved → baseline v1.1 (sheet 4). |  | 5-step CR process [03 §6.2 item 3]; proposed impact +22 h, +4,400,000 VND. |  | Pending
7 | Scrum event calendar | Sprint Planning ≤ 45 min on the first day of each Sprint; Daily Scrum ≤ 10 min, asynchronous in Slack #daily-standup (format Yesterday / Today / Blockers), logged; Review + Retro on Friday in class. |  | Timeboxes [03 §4.2]; Slack was the TA team channel. |  | Pending
8 | Configuration management | Branches main ← develop ← feat/Pxx-…, docs/Pxx-…; every change by PR reviewed by the other member; Conventional Commits + 'Refs: Pxx'; tags baseline-v1.0, baseline-v1.1 (if CR approved), v1.0. |  | No direct commits to main [03 §4.2]; criteria S5 and B7. |  | Pending
9 | Sprint 1 recovery | On 30/10 the Sprint 1 planning artefacts and F1 are not finished (sheet 2, status column). Finish and submit the S1 package as soon as possible, report the actual S1 result at Review 1, and re-check allocation at Sprint Planning 2 with the actual velocity. |  | Late penalty −10 % per 5 h [03 §4.2]; the Sprint timebox is fixed, so unfinished work returns to the backlog [Rubric 1, S2]. |  | Pending
[5 empty] | Approved: | 0/9
D. VERSION HISTORY
Version | Date | Author | Changes
0.1 | 30/10/2026 | Chính (drafted with Claude) | First draft as a Word document: schedule, milestones, Leader rotation, item allocation, velocity/PSP/BAC formulas.
0.2 | 30/10/2026 | Chính (drafted with Claude) | Workbook: WBS with owner, proposed hours and dates per task; BAC from the WBS; allocation; timeline; RACI; submission schedule; decisions for approval. vs. TA Work Plan: 2-week Sprint → three 1-week Sprints; scope → Release 1.0 (F1–F5).
0.3 | 30/10/2026 | Chính (drafted with Claude) | Capacity 28 h/person/Sprint (PO assumption); Planning Poker log in the BM01 format.
0.4 | 30/10/2026 | Chính (drafted with Claude) | Reorganised into the class Master Plan layout (proposal & approval, master schedule, item allocation, release plan, responsibilities, deliverables) + timeline and Planning Poker sheets; leader options compared; expected velocity now scaled from the TA reference velocity.
Legend: yellow cells = reviewer / team input. Story Points stay empty until the Planning Poker session; capacity and effort are planning assumptions, not actual hours (actual hours come from Jira Completed Work).

## 2_MasterSchedule
MASTER SCHEDULE & WBS 23/10 – 17/11/2026
WBS level 1 = Sprint/phase · level 2 = work package · level 3 = task (≤ 1 person-day). Effort = proposed person-hours (team to confirm); 'Both' = shared task, counted half per member. Status as of 30/10/2026.
WBS | Phase | Work package / task | Owner | Effort (h) | Output / evidence | Status | Planned start | Planned finish
1 | Sprint 1 | SPRINT 1 (Fri 23/10 – Thu 29/10) – Plan baseline & F1 ¦ Leader: Hồ Du Tuấn Đạt |  | 61.5 | Sprint Goal: an Administrator can create and lock accounts and a Customer can register, log in and log out, with admin functions blocked for every other role – F1 meets all its AC on the hosted URL; PMP v1.0 baselined. | 0% | 2026-10-23 | 2026-10-29
1.1 | Sprint 1 | Scrum events |  | 5.5 |  | 0% | 2026-10-23 | 2026-10-29
1.1.1 | Sprint 1 | Internal kick-off: Release 1.0 scope, roles, Leader rotation, working agreement, capacity | Both | 2 | Kick-off minutes; plan/INPUTS.md §1–2 | To Do | 2026-10-23 | 2026-10-24
1.1.2 | Sprint 1 | Sprint Planning 1 (≤ 45 min) → sheet S1_Backlog → Jira (Original Estimate) | Both | 1.5 | S1_Backlog; Jira Sprint 1 | To Do | 2026-10-24 | 2026-10-24
1.1.3 | Sprint 1 | Daily Scrum S1 (≤ 10 min, logged) + daily board and hours update | Both | 2 | Daily log; Jira Time spent | To Do | 2026-10-23 | 2026-10-29
1.2 | Sprint 1 | Project management – PMP v1.0 baseline |  | 29 |  | 0% | 2026-10-23 | 2026-10-29
1.2.1 | Sprint 1 | Repo structure, develop/main branches, roadmap; repo private; invite lecturer to GitHub and Jira (Viewer) | Hồ Du Tuấn Đạt | 2 | Repo; access confirmation | In Progress | 2026-10-23 | 2026-10-27
1.2.2 | Sprint 1 | Product Backlog v1.0: remap v0 to F1–F5, Given–When–Then AC, MoSCoW, Definition of Ready | Nguyễn Minh Chính | 4 | pm/backlog/product-backlog.md | To Do | 2026-10-24 | 2026-10-26
1.2.3 | Sprint 1 | Planning Poker session for new/changed items + log of every round | Both | 2 | Planning Poker log + photo evidence | To Do | 2026-10-26 | 2026-10-26
1.2.4 | Sprint 1 | Master Plan / Release Plan: schedule, milestones, allocation, capacity, velocity, PSP, BAC | Nguyễn Minh Chính | 3 | This workbook; PMP part 3 | In Progress | 2026-10-24 | 2026-10-26
1.2.5 | Sprint 1 | PMP part 1 – Project Charter (Lab 1–2 updated to Release 1.0) | Nguyễn Minh Chính | 2 | PMP part 1 | To Do | 2026-10-25 | 2026-10-27
1.2.6 | Sprint 1 | PMP part 2 – Tailored Scrum process (TA Process updated to 1-week Sprints) | Hồ Du Tuấn Đạt | 2 | PMP part 2 | To Do | 2026-10-25 | 2026-10-27
1.2.7 | Sprint 1 | PMP part 4 – Quality plan (3-level DoD with evidence and checker, metrics) | Nguyễn Minh Chính | 2 | PMP part 4 | To Do | 2026-10-26 | 2026-10-28
1.2.8 | Sprint 1 | PMP part 5 – Risk management plan (P×I 1–5, register ≥ 8 risks) | Hồ Du Tuấn Đạt | 2 | PMP part 5 | To Do | 2026-10-26 | 2026-10-28
1.2.9 | Sprint 1 | PMP parts 6–7 – Configuration management plan, Communication plan | Hồ Du Tuấn Đạt | 2 | PMP parts 6–7 | To Do | 2026-10-26 | 2026-10-28
◆ | Sprint 1 | ◆ Tue 27/10 in class: Change Request CR-06 received | Nguyễn Minh Chính | 0 | CR-06 form | Done | 2026-10-27 | 2026-10-27
1.2.10 | Sprint 1 | CR-06: record in Change Log, impact analysis, ≥ 2 options for the CCB | Nguyễn Minh Chính | 3 | pm/change/change-log.md, CR-06-impact-analysis.md | In Progress | 2026-10-27 | 2026-10-29
1.2.11 | Sprint 1 | Consolidate c1_ProjectPlan.docx and c2_SprintBacklog_S1.xlsx | Hồ Du Tuấn Đạt | 3 | c1, c2 – Sprint 1 | To Do | 2026-10-28 | 2026-10-29
1.2.12 | Sprint 1 | c3_SprintReport_S1 + c0_Eval_S1 + upload each file to E-learning | Hồ Du Tuấn Đạt | 2 | c3, c0 – Sprint 1 | To Do | 2026-10-29 | 2026-10-29
1.3 | Sprint 1 | Development – F1 and foundations |  | 21 |  | 0% | 2026-10-24 | 2026-10-28
1.3.1 | Sprint 1 | Scaffold app (Next.js, PostgreSQL, health check) and deploy to free hosting (NFR-02) | Hồ Du Tuấn Đạt | 4 | Public URL; app/README.md | To Do | 2026-10-24 | 2026-10-25
1.3.2 | Sprint 1 | US-01 Register – API, server validation, password hashing | Hồ Du Tuấn Đạt | 3 | Reviewed PR | To Do | 2026-10-25 | 2026-10-26
1.3.3 | Sprint 1 | US-01 Register – form and client validation | Nguyễn Minh Chính | 2 | Reviewed PR | To Do | 2026-10-25 | 2026-10-26
1.3.4 | Sprint 1 | US-02 Log in / log out – API and session | Hồ Du Tuấn Đạt | 3 | Reviewed PR | To Do | 2026-10-26 | 2026-10-27
1.3.5 | Sprint 1 | US-02 Log in / log out – screens | Nguyễn Minh Chính | 2 | Reviewed PR | To Do | 2026-10-26 | 2026-10-27
1.3.6 | Sprint 1 | US-03 Roles (Administrator, Customer) + server-side authorization guard | Hồ Du Tuấn Đạt | 3 | Reviewed PR | To Do | 2026-10-27 | 2026-10-28
1.3.7 | Sprint 1 | US-03 Administrator creates and locks accounts (screens + API) | Nguyễn Minh Chính | 4 | Reviewed PR | To Do | 2026-10-27 | 2026-10-28
1.4 | Sprint 1 | Testing – F1 |  | 6 |  | 0% | 2026-10-25 | 2026-10-29
1.4.1 | Sprint 1 | Write F1 test cases from the AC (≥ 1 per AC) | Nguyễn Minh Chính | 2 | pm/sprints/S1/test-cases-F1.md | To Do | 2026-10-27 | 2026-10-28
1.4.2 | Sprint 1 | Execute F1 test cases on the hosted URL; record actual results and defects | Nguyễn Minh Chính | 2 | Test results | To Do | 2026-10-28 | 2026-10-29
1.4.3 | Sprint 1 | Code review of F1 pull requests (each reviews the other) | Both | 2 | PR reviews | To Do | 2026-10-25 | 2026-10-29
M3 | Sprint 1 | ◆ SPRINT 1 SUBMISSION – 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | 0 | Upload each file separately to E-learning; no zip |  | 2026-10-29 | 2026-10-29
2 | Sprint 2 | SPRINT 2 (Fri 30/10 – Thu 05/11) – Execution, monitoring & change control ¦ Leader: Nguyễn Minh Chính (PO) |  | 53.5 | Sprint Goal: an Administrator can manage books (soft delete), categories and authors, and a Customer can browse a responsive grid of ≥ 30 books, 12 per page, newest first – F2 and F3 meet all their AC; CR-06 processed through the CCB. | 0% | 2026-10-30 | 2026-11-05
2.1 | Sprint 2 | Scrum events |  | 5.5 |  | 0% | 2026-10-30 | 2026-11-05
2.1.1 | Sprint 2 | ◆ Review & Retro 1 in class, Fri 30/10 (Đạt presents; ≥ 2 action items) | Both | 2 | Review slides; Retro action items | To Do | 2026-10-30 | 2026-10-30
2.1.2 | Sprint 2 | Sprint Planning 2 with the ACTUAL Sprint 1 velocity → S2_Backlog → Jira | Both | 1.5 | S2_Backlog; Jira Sprint 2 | To Do | 2026-10-30 | 2026-10-30
2.1.3 | Sprint 2 | Daily Scrum S2 + daily board and hours update | Both | 2 | Daily log; Jira Time spent | To Do | 2026-10-30 | 2026-11-05
2.2 | Sprint 2 | Project management & change control |  | 11 |  | 0% | 2026-10-30 | 2026-11-05
2.2.1 | Sprint 2 | CCB on CR-06 (PO + Leader + Sponsor): record decision and reasons | Nguyễn Minh Chính | 1 | CCB record; plan/INPUTS.md §5 | To Do | 2026-10-30 | 2026-10-30
2.2.2 | Sprint 2 | If approved: rebaseline backlog, AC, Release Plan v1.1, risk register; tag baseline-v1.1; inform stakeholders | Nguyễn Minh Chính | 3 | Rebaselined plan + tag | To Do | 2026-10-30 | 2026-10-31
2.2.3 | Sprint 2 | c4_ChangeRequest_CR01 form (impact analysis, CCB decision, baseline update) | Nguyễn Minh Chính | 2 | c4_ChangeRequest_CR01.docx | To Do | 2026-11-02 | 2026-11-05
2.2.4 | Sprint 2 | Weekly Status Report; update Risk Register and Issue Log | Nguyễn Minh Chính | 2 | Status report; risk/issue log | To Do | 2026-11-03 | 2026-11-05
2.2.5 | Sprint 2 | c2_SprintBacklog_S2 + c3_SprintReport_S2 + c0_Eval_S2 + upload | Nguyễn Minh Chính | 3 | c2, c3, c0 – Sprint 2 | To Do | 2026-11-04 | 2026-11-05
2.3 | Sprint 2 | Development – F2 and F3 |  | 29 |  | 0% | 2026-10-31 | 2026-11-04
2.3.1 | Sprint 2 | Data model: books, categories, authors (hidden flag for soft delete) | Hồ Du Tuấn Đạt | 3 | Reviewed PR; migration | To Do | 2026-10-31 | 2026-10-31
2.3.2 | Sprint 2 | US-24 Manage categories (API + screens + validation) | Nguyễn Minh Chính | 3 | Reviewed PR | To Do | 2026-10-31 | 2026-11-01
2.3.3 | Sprint 2 | US-25 Manage authors (API + screens + validation) | Nguyễn Minh Chính | 3 | Reviewed PR | To Do | 2026-11-01 | 2026-11-02
2.3.4 | Sprint 2 | US-08 Add book – API and server validation (price > 0, required fields) | Hồ Du Tuấn Đạt | 3 | Reviewed PR | To Do | 2026-10-31 | 2026-11-01
2.3.5 | Sprint 2 | US-08 Add book – form, cover image, client validation | Nguyễn Minh Chính | 3 | Reviewed PR | To Do | 2026-11-01 | 2026-11-02
2.3.6 | Sprint 2 | US-09 Edit book | Hồ Du Tuấn Đạt | 2 | Reviewed PR | To Do | 2026-11-02 | 2026-11-02
2.3.7 | Sprint 2 | US-10 Delete book = hide (no hard delete) | Hồ Du Tuấn Đạt | 2 | Reviewed PR | To Do | 2026-11-02 | 2026-11-03
2.3.8 | Sprint 2 | NFR-01 Seed ≥ 30 sample books | Hồ Du Tuấn Đạt | 2 | Seed script | To Do | 2026-11-02 | 2026-11-03
2.3.9 | Sprint 2 | US-05 Book list – card grid (cover, title, author, price), responsive | Nguyễn Minh Chính | 3 | Reviewed PR | To Do | 2026-11-02 | 2026-11-03
2.3.10 | Sprint 2 | US-05 Pagination 12 per page, newest first; measure list load < 2 s | Hồ Du Tuấn Đạt | 3 | Reviewed PR; timing evidence | To Do | 2026-11-03 | 2026-11-04
2.3.11 | Sprint 2 | US-21 Responsive and cross-browser check (desktop, tablet, phone) | Hồ Du Tuấn Đạt | 2 | Screenshots | To Do | 2026-11-04 | 2026-11-04
2.4 | Sprint 2 | Testing – F2 and F3 |  | 8 |  | 0% | 2026-10-31 | 2026-11-05
2.4.1 | Sprint 2 | Write F2 and F3 test cases from the AC | Hồ Du Tuấn Đạt | 3 | Test cases F2, F3 | To Do | 2026-11-02 | 2026-11-04
2.4.2 | Sprint 2 | Execute F2/F3 test cases + F1 regression; record actual results | Hồ Du Tuấn Đạt | 3 | Test results | To Do | 2026-11-04 | 2026-11-05
2.4.3 | Sprint 2 | Code review of F2/F3 pull requests | Both | 2 | PR reviews | To Do | 2026-10-31 | 2026-11-05
M5 | Sprint 2 | ◆ SPRINT 2 SUBMISSION – 23:59 Thu 05/11 | Nguyễn Minh Chính | 0 | Upload each file separately to E-learning; no zip |  | 2026-11-05 | 2026-11-05
3 | Sprint 3 | SPRINT 3 (Fri 06/11 – Thu 12/11) – Complete Release 1.0 & acceptance ¦ Leader: Hồ Du Tuấn Đạt |  | 37.5 | Sprint Goal: a Customer can open a book's details and search/filter the catalogue together with pagination – F4 and F5 meet all their AC, F1–F3 pass regression, v1.0 is tagged and ready for UAT. | 0% | 2026-11-06 | 2026-11-12
3.1 | Sprint 3 | Scrum events |  | 5.5 |  | 0% | 2026-11-06 | 2026-11-12
3.1.1 | Sprint 3 | ◆ Review & Retro 2 in class, Fri 06/11 (Chính presents) | Both | 2 | Review slides; Retro action items | To Do | 2026-11-06 | 2026-11-06
3.1.2 | Sprint 3 | Sprint Planning 3 with the ACTUAL Sprint 2 velocity → S3_Backlog → Jira | Both | 1.5 | S3_Backlog; Jira Sprint 3 | To Do | 2026-11-06 | 2026-11-06
3.1.3 | Sprint 3 | Daily Scrum S3 + daily board and hours update | Both | 2 | Daily log; Jira Time spent | To Do | 2026-11-06 | 2026-11-12
3.2 | Sprint 3 | Project management & release |  | 10 |  | 0% | 2026-11-09 | 2026-11-12
3.2.1 | Sprint 3 | UAT script mapped to every AC (incl. CR-06 if approved) | Nguyễn Minh Chính | 3 | pm/uat/uat-script.md | To Do | 2026-11-09 | 2026-11-12
3.2.2 | Sprint 3 | Release v1.0: PR develop → main, tag v1.0, release notes | Hồ Du Tuấn Đạt | 2 | Tag v1.0; release notes | To Do | 2026-11-11 | 2026-11-12
3.2.3 | Sprint 3 | EVM draft (PV, EV, AC, SV, CV, SPI, CPI, EAC, ETC) from Jira hours | Nguyễn Minh Chính | 2 | EVM sheet (draft) | To Do | 2026-11-10 | 2026-11-12
3.2.4 | Sprint 3 | c2_SprintBacklog_S3 + c3_SprintReport_S3 + c5_UAT + c0_Eval_S3 + upload | Hồ Du Tuấn Đạt | 3 | c2, c3, c5, c0 – Sprint 3 | To Do | 2026-11-11 | 2026-11-12
3.3 | Sprint 3 | Development – F4 and F5 |  | 14 |  | 0% | 2026-11-07 | 2026-11-10
3.3.1 | Sprint 3 | US-07 Book details page (API + screen) | Nguyễn Minh Chính | 3 | Reviewed PR | To Do | 2026-11-07 | 2026-11-08
3.3.2 | Sprint 3 | US-07 Unknown ID → friendly message; Back returns to the same list page | Nguyễn Minh Chính | 2 | Reviewed PR | To Do | 2026-11-08 | 2026-11-09
3.3.3 | Sprint 3 | US-06 Search by title or author (API) | Hồ Du Tuấn Đạt | 3 | Reviewed PR | To Do | 2026-11-07 | 2026-11-08
3.3.4 | Sprint 3 | US-06 Filter by category and price range (API) | Hồ Du Tuấn Đạt | 3 | Reviewed PR | To Do | 2026-11-08 | 2026-11-09
3.3.5 | Sprint 3 | US-06 Search/filter screen working with pagination (state kept in the URL) | Nguyễn Minh Chính | 3 | Reviewed PR | To Do | 2026-11-09 | 2026-11-10
3.4 | Sprint 3 | Testing – F4 and F5 |  | 8 |  | 0% | 2026-11-07 | 2026-11-11
3.4.1 | Sprint 3 | Write F4 and F5 test cases from the AC | Nguyễn Minh Chính | 2 | Test cases F4, F5 | To Do | 2026-11-08 | 2026-11-10
3.4.2 | Sprint 3 | Execute F4/F5 test cases + regression F1–F3 + list < 2 s check; fix defects | Hồ Du Tuấn Đạt | 4 | Test results; defect log | To Do | 2026-11-10 | 2026-11-11
3.4.3 | Sprint 3 | Code review of F4/F5 pull requests | Both | 2 | PR reviews | To Do | 2026-11-07 | 2026-11-11
M7 | Sprint 3 | ◆ RELEASE v1.0 + SPRINT 3 SUBMISSION – 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | 0 | Upload each file separately to E-learning; no zip |  | 2026-11-12 | 2026-11-12
4 | Closure | CONSOLIDATION & CLOSURE (Fri 13/11 – Tue 17/11) ¦ Whole team |  | 18 | Goal: Release 1.0 accepted at UAT and online until 17/11; final package submitted on time; every member presents. | 0% | 2026-11-13 | 2026-11-17
4.1 | Closure | Acceptance and hand-over |  | 4 |  | 0% | 2026-11-13 | 2026-11-14
4.1.1 | Closure | ◆ Review 3 + UAT with the customer; acceptance record | Both | 2 | Signed acceptance record | To Do | 2026-11-13 | 2026-11-13
4.1.2 | Closure | Final hosting check, demo accounts (admin, customer), closure data | Hồ Du Tuấn Đạt | 2 | URL; demo accounts; closure data | To Do | 2026-11-13 | 2026-11-14
4.2 | Closure | Closure documents and presentation |  | 14 |  | 0% | 2026-11-13 | 2026-11-17
4.2.1 | Closure | Final Report: plan vs. actual, EVM, risks & changes, closure checklist, Lessons Learned ≥ 5, AI declaration | Nguyễn Minh Chính | 4 | c6_FinalReport.docx | To Do | 2026-11-13 | 2026-11-15
4.2.2 | Closure | PMP Final + Workbook Final (EVM sheet) | Hồ Du Tuấn Đạt | 3 | c1_ProjectPlan_Final, c2_SprintBacklog_Final | To Do | 2026-11-13 | 2026-11-15
4.2.3 | Closure | Slides (font ≥ 20 pt) + demo video ≤ 3 min (pass and fail AC) | Both | 4 | c6_Slides; video link | To Do | 2026-11-14 | 2026-11-15
4.2.4 | Closure | Final submission + one Eval360 file per member | Both | 1 | All final files | To Do | 2026-11-15 | 2026-11-15
4.2.5 | Closure | Rehearsal; keep the website online until the end of 17/11 | Both | 2 | Rehearsal notes | To Do | 2026-11-16 | 2026-11-17
M10 | Closure | ◆ FINAL PRESENTATION – 07:00 Tue 17/11 | Both | 0 |  |  | 2026-11-17 | 2026-11-17
|  | Total effort Sprints 1–3 (h) – basis of BAC |  | 152.5
|  | Closure effort (h) – after Sprint 3, outside BAC (PV is defined over N = 3 Sprints) |  | 18
Formulas:
Planned start = MIN([Planned start, row below]:H36)
Planned finish = MAX([Planned finish, row below]:I36)

## 3_ItemAllocation
PRODUCT BACKLOG ALLOCATION PER SPRINT (proposed rebaseline v0 → v1.0)
IDs kept from TA Product Backlog v0 (23 items, 99 SP); new items numbered from US-24. SP = final Planning Poker result from sheet 8 (empty until the session is held).
US ID | Feature | Epic | User Story (short) | SP | MoSCoW | Sprint | Main developer | Change vs. previous backlog (v0 SP in brackets)
US-01 | F1 | EP-01 User Accounts | Customer registers with email and password; hashed password; client + server validation |  | Must | Sprint 1 | Hồ Du Tuấn Đạt | Changed – email confirmation dropped (not in F1); hashing and validation added → re-estimate [v0: 3 SP]
US-02 | F1 | EP-01 User Accounts | User logs in and logs out |  | Must | Sprint 1 | Hồ Du Tuấn Đạt | Changed – password reset/lockout not required by F1 (PO to confirm) → re-estimate [v0: 3 SP]
US-03 | F1 | EP-01 User Accounts | Administrator creates and locks accounts; roles Administrator / Customer; admin functions blocked on the server |  | Must | Sprint 1 | Nguyễn Minh Chính | Rewritten – Store Manager/Staff roles removed from R1.0 [05 #6] → re-estimate [v0: 5 SP]
NFR-02 | NFR | EP-08 Quality (NFR) | Release hosted on a free server, reachable by the lecturer, online until 17/11 |  | Must | Sprint 1 | Hồ Du Tuấn Đạt | New – deployed in Sprint 1 so every Increment is demonstrated online [new]
US-08 | F2 | EP-03 Book Management | Administrator adds a book: title, author, category, price > 0, description, cover image, stock |  | Must | Sprint 2 | Hồ Du Tuấn Đạt | Changed – mandatory ISBN dropped, description/stock added → re-estimate [v0: 5 SP]
US-09 | F2 | EP-03 Book Management | Administrator edits book information |  | Must | Sprint 2 | Hồ Du Tuấn Đạt | Kept – price-change log removed [v0: 3 SP]
US-10 | F2 | EP-03 Book Management | Administrator deletes a book = hidden, no hard delete |  | Must | Sprint 2 | Hồ Du Tuấn Đạt | Kept [v0: 2 SP]
US-24 | F2 | EP-03 Book Management | Administrator manages categories |  | Must | Sprint 2 | Nguyễn Minh Chính | New – required by F2 [05 #5] [new]
US-25 | F2 | EP-03 Book Management | Administrator manages authors |  | Must | Sprint 2 | Nguyễn Minh Chính | New – required by F2 [05 #5] [new]
US-05 | F3 | EP-02 Book Catalog | Customer browses a card grid (cover, title, author, price), 12 per page, newest first |  | Must | Sprint 2 | Nguyễn Minh Chính | Changed – 20 → 12 per page; sort options removed [05 #2] → re-estimate [v0: 3 SP]
NFR-01 | F3 | EP-08 Quality (NFR) | ≥ 30 sample books; list page loads in < 2 s |  | Must | Sprint 2 | Hồ Du Tuấn Đạt | New [05 #8] [new]
US-21 | NFR | EP-08 Quality (NFR) | Responsive, cross-browser layout (desktop, tablet, phone) |  | Must | Sprint 2 | Hồ Du Tuấn Đạt | Kept – checked with F3; PO may move it into the Story DoD [05 #9] [v0: 5 SP]
US-07 | F4 | EP-02 Book Catalog | Book details page; unknown ID → friendly message; Back returns to the same list page |  | Must | Sprint 3 | Nguyễn Minh Chính | Changed – 'Add to cart' removed; 2 AC added [05 #4] → re-estimate [v0: 3 SP]
US-06 | F5 | EP-02 Book Catalog | Search by title or author; filter by category and price range; works with pagination |  | Must | Sprint 3 | Hồ Du Tuấn Đạt | Changed – ISBN/genre removed; price range + pagination added [05 #3] → re-estimate [v0: 5 SP]
US-26 | F1, F2 | EP-01 User Accounts | CR-06: Store Staff role and permissions |  | CCB decides | CR-06 | Hồ Du Tuấn Đạt | Change Request – only after CCB approval (baseline v1.1) [new]
US-27 | F2 | EP-03 Book Management | CR-06: book shows 'Last updated by … at …' |  | CCB decides | CR-06 | Hồ Du Tuấn Đạt | Change Request – only after CCB approval (baseline v1.1) [new]
US-04 | — | EP-01 User Accounts | Profile and delivery addresses |  | Won't (R1.0) | Future |  | Depends on checkout – out of R1.0 scope [v0: 2 SP]
US-11 | — | EP-04 Cart & Checkout | Shopping cart |  | Won't (R1.0) | Future |  | Out of scope per the spec [03 §2.2] [v0: 5 SP]
US-12 | — | EP-04 Cart & Checkout | Checkout and online payment |  | Won't (R1.0) | Future |  | Out of scope per the spec [03 §2.2] [v0: 8 SP]
US-13 | — | EP-04 Cart & Checkout | Order history and tracking |  | Won't (R1.0) | Future |  | Depends on orders [v0: 3 SP]
US-14 | — | EP-04 Cart & Checkout | Staff process orders |  | Won't (R1.0) | Future |  | Depends on orders [v0: 5 SP]
US-15 | — | EP-05 Promotions | Create promotions |  | Won't (R1.0) | Future |  | Not in F1–F5 [v0: 5 SP]
US-16 | — | EP-05 Promotions | Apply a promotion code at checkout |  | Won't (R1.0) | Future |  | Depends on checkout [v0: 3 SP]
US-17 | — | EP-06 Multi-store | Manage stores and stock per store |  | Won't (R1.0) | Future |  | Not in F1–F5 [v0: 8 SP]
US-18 | — | EP-06 Multi-store | Store availability and pickup |  | Won't (R1.0) | Future |  | Not in F1–F5 [v0: 5 SP]
US-19 | — | EP-07 Customer Engagement | Ratings and reviews |  | Won't (R1.0) | Future |  | Requires purchase data [v0: 5 SP]
US-20 | — | EP-07 Customer Engagement | Wishlist |  | Won't (R1.0) | Future |  | Not in F1–F5 [v0: 2 SP]
US-22 | — | EP-08 Quality (NFR) | Distinctive brand theme |  | Won't (R1.0) | Future |  | PO to decide – 'own style' partly covered by the UI design [v0: 3 SP]
US-23 | — | EP-07 Customer Engagement | Book recommendations |  | Won't (R1.0) | Future |  | Already Won't in v0 [v0: 8 SP]
Summary
|  |  | Sprint | SP | Items
|  |  | Sprint 1 | TBD | 4
|  |  | Sprint 2 | TBD | 8
|  |  | Sprint 3 | TBD | 2
|  |  | CR-06 | TBD | 2
|  |  | Future | — | 13
|  |  | Release 1.0 total (PSP) = Sprints 1–3 | TBD | 14
|  |  | Total backlog items (required ≥ 15) |  | 29 | Met

## 4_ReleasePlan
RELEASE PLAN, CAPACITY & BUDGET (BAC)
Yellow = editable assumptions/inputs; blue = sourced constants; all other cells are formulas.
Assumptions
Team members | 2 | Hồ Du Tuấn Đạt, Nguyễn Minh Chính
Hours / person / Sprint (planned capacity) | 28 | Assumption set by the PO on 30/10/2026: 4 h per day × 7 days (same daily figure as the TA Work Plan, Assign.xlsx). Đạt to confirm.
Number of Sprints (N) | 3 | Per the spec [03 §5]
Rate (VND / person-hour) | 200000 | Per the spec – AgileEVM [03 §6.4]
Reference velocity (SP per TA Sprint) | 22 | TA Sprint 1 plan: 22 SP selected against 80 h team capacity (2 people × 10 days × 4 h) [04 §5]
Reference capacity of that Sprint (h) | 80 | [04 §5]
Expected velocity (SP / Sprint) | 15.4 | Reference velocity × team capacity ÷ reference capacity. Replaced by the ACTUAL velocity from Sprint 2 planning on [03 §6.2 item 1]
Plan per Sprint
Sprint | Dates | Leader | Sprint Goal | Features | Planned SP | Capacity (h) | WBS planned effort (h) | Hours / SP | Cumulative PV (VND) | SP vs. velocity | Hours vs. capacity
Sprint 1 | 23/10 – 29/10 | Hồ Du Tuấn Đạt | Sprint Goal: an Administrator can create and lock accounts and a Customer can register, log in and log out, with admin functions blocked for every other role – F1 meets all its AC on the hosted URL; PMP v1.0 baselined. | F1 + hosting | TBD | 56 | 61.5 | TBD | 10166666.6667 | TBD | Over capacity
Sprint 2 | 30/10 – 05/11 | Nguyễn Minh Chính (PO) | Sprint Goal: an Administrator can manage books (soft delete), categories and authors, and a Customer can browse a responsive grid of ≥ 30 books, 12 per page, newest first – F2 and F3 meet all their AC; CR-06 processed through the CCB. | F2, F3 (+ CR-06 if approved) | TBD | 56 | 53.5 | TBD | 20333333.3333 | TBD | Within capacity
Sprint 3 | 06/11 – 12/11 | Hồ Du Tuấn Đạt | Sprint Goal: a Customer can open a book's details and search/filter the catalogue together with pagination – F4 and F5 meet all their AC, F1–F3 pass regression, v1.0 is tagged and ready for UAT. | F4, F5 + Release v1.0 | TBD | 56 | 37.5 | TBD | 30500000 | TBD | Within capacity
Total |  |  |  |  | TBD | 168 | 152.5
Baseline metrics
Metric | Value | Formula / note
BAC (VND) = total WBS planned hours (Sprints 1–3) × rate | 30500000 | Effort hours are proposals (sheet 2) – team to confirm
PSP – total planned Story Points of Release 1.0 | TBD | TBD until the Planning Poker session (sheet 8)
PSP matches sheet 3 | Match
Average planned hours / SP | TBD
Closure effort (h) – outside BAC | 18 | 13/11 – 17/11, after the 3 Sprints
Rebaseline after CR-06 (only if the CCB approves)
Item | Value | Source / note
CCB decision | Pending | Approved / Rejected / Deferred – enter after the CCB
CR-06 hours added | 22 | Proposed in pm/change/CR-06-impact-analysis.md §5 – update after the CCB
BAC v1.1 (VND) | n/a | Baseline v1.0 is kept; v1.1 is added [03 §6.2 item 3]
PSP v1.1 (SP) | n/a
Note: Sprint Planning 2 and 3 use the ACTUAL velocity of the previous Sprint, not the expected figure [03 §6.2 item 1]. A 2-member team adjusts capacity and the plan, never the F1–F5 scope [03 §2.2].

## 5_Responsibilities
ROLES & DOCUMENT RESPONSIBILITIES
A = accountable (one per row) · R = does the work · C = consulted / reviews · I = informed
Item | Hồ Du Tuấn Đạt | Nguyễn Minh Chính | Notes
Scrum role | Developer; Sprint Leader S1, S3 | Product Owner + Developer; Sprint Leader S2 | Fixed PO, rotating Leader [03 §4.1]
PMP 1 – Project Charter | C | A/R | From Lab 1–2 (Chính was Project Lead / BA)
PMP 2 – Tailored Scrum process | A/R | C | From TA Process.docx
PMP 3 – Master / Release Plan | C | A/R | This workbook
PMP 4 – Quality plan (3-level DoD, metrics) | C | A/R | PO accepts Done items
PMP 5 – Risk management plan | A/R | C | Risks reviewed every Sprint
PMP 6 – Configuration management plan | A/R | C | Repo owner
PMP 7 – Communication plan | A/R | C | From Lab 1 §4 (Đạt) and Assign.xlsx
Product Backlog, AC, Definition of Ready | C | A/R | PO orders the backlog
Planning Poker (log + evidence) | R | A/R | Both vote; PO reads the stories
Sprint Backlog + Jira (each Sprint) | A/R in S1, S3 | A/R in S2 | Sprint Leader keeps the board current
Change Request CR-06 & CCB | R (reviews impact analysis) | A/R (PO in the CCB) | Sponsor decides
Rebaseline + configuration tags | R (tags) | A/R | baseline-v1.0, baseline-v1.1, v1.0
Test cases from AC | R (F2, F3) | A/R (F1, F4, F5) | ≥ 1 test case per AC
UAT script & acceptance record | C | A/R | Run at Review 3 (13/11)
Hosting & Release v1.0 | A/R | C | Tag v1.0 + release notes
EVM & Final Report | R (PMP / Workbook Final) | A/R (Final Report, EVM) | Hours from Jira Completed Work
Slides & demo video | R | A/R | Everyone presents
Member evaluation c0_Eval | Sprint 1, Sprint 3 | Sprint 2 | Sprint Leader evaluates members
Development Story Points per person (main developer, sheet 3)
Member | Sprint 1 | Sprint 2 | Sprint 3 | Total SP
Hồ Du Tuấn Đạt | 0 | 0 | 0 | 0
Nguyễn Minh Chính | 0 | 0 | 0 | 0
Planned hours per person (sheet 2, 'Both' split 50/50) vs. capacity
Member | Sprint 1 | Sprint 2 | Sprint 3 | Closure
Hồ Du Tuấn Đạt | 30.75 | 26.75 | 18.75 | 9.5
Nguyễn Minh Chính | 30.75 | 26.75 | 18.75 | 8.5
Capacity per person (h) | 28 | 28 | 28
Hồ Du Tuấn Đạt – check | Over capacity | OK | OK
Nguyễn Minh Chính – check | Over capacity | OK | OK

## 6_Deliverables
SUBMISSION SCHEDULE & FILE NAMES
Prefix HK261_SPM_FP_Team6_ · upload files individually, no zip · Excel files are cumulative · late: −10 % of the Sprint score per 5 h [03 §4.2, §7]
Submission | Due | Submitted by | File name | Content | Submitted?
eLearning item | 26/10 19:35 (late) | Nguyễn Minh Chính | HK261_SPM_FP_Team6_MasterPlan.xlsx | FinalProject: Master Plan and Timeline – this workbook | No
Sprint 1 | 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c1_ProjectPlan.docx | PMP v1.0 (7 parts) | No
Sprint 1 | 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c2_SprintBacklog_S1.xlsx | Product Backlog, Planning Poker log, Release Plan, Sprint Backlog S1, Burndown, Risk Register, Config Items | No
Sprint 1 | 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c3_SprintReport_S1.docx | Sprint Planning, Daily log, F1 test cases, Review, Retro, Status | No
Sprint 1 | 23:59 Thu 29/10 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c0_Eval_S1.xlsx | Leader evaluates members | No
Sprint 2 | 23:59 Thu 05/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c2_SprintBacklog_S2.xlsx | Updated workbook (Change Log, Risk, Issue Log, S2) | No
Sprint 2 | 23:59 Thu 05/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c3_SprintReport_S2.docx | Sprint 2 report + F2, F3 test cases + Weekly Status | No
Sprint 2 | 23:59 Thu 05/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c4_ChangeRequest_CR01.docx | CR form, impact analysis, CCB decision (CR01 vs CR06 file name: ask the lecturer) | No
Sprint 2 | 23:59 Thu 05/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c0_Eval_S2.xlsx | Leader evaluates members | No
Sprint 3 | 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c2_SprintBacklog_S3.xlsx | Updated workbook (S3, draft EVM) | No
Sprint 3 | 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c3_SprintReport_S3.docx | Sprint 3 report + F4, F5 test cases + release notes | No
Sprint 3 | 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c5_UAT.docx | UAT scripts and acceptance record | No
Sprint 3 | 23:59 Thu 12/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c0_Eval_S3.xlsx | Leader evaluates members | No
Final | 23:59 Sun 15/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c1_ProjectPlan_Final.docx | PMP updated after lecturer feedback and the CR | No
Final | 23:59 Sun 15/11 | Hồ Du Tuấn Đạt | HK261_SPM_FP_Team6_c2_SprintBacklog_Final.xlsx | Complete workbook incl. EVM sheet | No
Final | 23:59 Sun 15/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c6_FinalReport.docx | Final Report + Lessons Learned + hosted URL + repo/board/video links | No
Final | 23:59 Sun 15/11 | Nguyễn Minh Chính | HK261_SPM_FP_Team6_c6_Slides.pptx | Final presentation slides | No
Final | 23:59 Sun 15/11 | Each member | Eval360_Team6_<StudentID>.xlsx | One 360° evaluation file per member | No
Final presentation: 07:00 Tuesday 17/11/2026 – 10 min + 5 min Q&A; every member presents [03 §8].

## 7_Timeline
TIMELINE 23/10 – 17/11/2026
Bars come from the planned dates in sheet 2. Navy = Sprint/phase · grey = work package · black = milestone · today's column is outlined in red.
WBS | Item | Start | Finish | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17
1 | SPRINT 1 (Fri 23/10 – Thu 29/10) – Plan baseline & F1 ¦ Leader: Hồ Du Tuấn Đạt | 2026-10-23 | 2026-10-29 | [26 empty] | L1
1.1 | Scrum events | 2026-10-23 | 2026-10-29 | [26 empty] | L2
1.2 | Project management – PMP v1.0 baseline | 2026-10-23 | 2026-10-29 | [26 empty] | L2
1.3 | Development – F1 and foundations | 2026-10-24 | 2026-10-28 | [26 empty] | L2
1.4 | Testing – F1 | 2026-10-25 | 2026-10-29 | [26 empty] | L2
M3 | ◆ SPRINT 1 SUBMISSION – 23:59 Thu 29/10 | 2026-10-29 | 2026-10-29 | [26 empty] | MS
2 | SPRINT 2 (Fri 30/10 – Thu 05/11) – Execution, monitoring & change control ¦ Leader: Nguyễn Minh Chính (PO) | 2026-10-30 | 2026-11-05 | [26 empty] | L1
2.1 | Scrum events | 2026-10-30 | 2026-11-05 | [26 empty] | L2
2.2 | Project management & change control | 2026-10-30 | 2026-11-05 | [26 empty] | L2
2.3 | Development – F2 and F3 | 2026-10-31 | 2026-11-04 | [26 empty] | L2
2.4 | Testing – F2 and F3 | 2026-10-31 | 2026-11-05 | [26 empty] | L2
M5 | ◆ SPRINT 2 SUBMISSION – 23:59 Thu 05/11 | 2026-11-05 | 2026-11-05 | [26 empty] | MS
3 | SPRINT 3 (Fri 06/11 – Thu 12/11) – Complete Release 1.0 & acceptance ¦ Leader: Hồ Du Tuấn Đạt | 2026-11-06 | 2026-11-12 | [26 empty] | L1
3.1 | Scrum events | 2026-11-06 | 2026-11-12 | [26 empty] | L2
3.2 | Project management & release | 2026-11-09 | 2026-11-12 | [26 empty] | L2
3.3 | Development – F4 and F5 | 2026-11-07 | 2026-11-10 | [26 empty] | L2
3.4 | Testing – F4 and F5 | 2026-11-07 | 2026-11-11 | [26 empty] | L2
M7 | ◆ RELEASE v1.0 + SPRINT 3 SUBMISSION – 23:59 Thu 12/11 | 2026-11-12 | 2026-11-12 | [26 empty] | MS
4 | CONSOLIDATION & CLOSURE (Fri 13/11 – Tue 17/11) ¦ Whole team | 2026-11-13 | 2026-11-17 | [26 empty] | L1
4.1 | Acceptance and hand-over | 2026-11-13 | 2026-11-14 | [26 empty] | L2
4.2 | Closure documents and presentation | 2026-11-13 | 2026-11-17 | [26 empty] | L2
M10 | ◆ FINAL PRESENTATION – 07:00 Tue 17/11 | 2026-11-17 | 2026-11-17 | [26 empty] | MS

## 8_PlanningPoker
PLANNING POKER LOG – Release 1.0 (lecturer template BM01)
Fill DURING the session with the real cards. Fibonacci 1, 2, 3, 5, 8, 13 (split items > 13); reveal together; highest and lowest voters explain; max 3 rounds; still different → take the higher value. Evidence photo: pm/backlog/evidence/.
Session date/time | [6 empty] | # | Member | Role
Channel / place | [6 empty] | 1 | Hồ Du Tuấn Đạt | Developer · Sprint Leader S1, S3
Facilitator | Nguyễn Minh Chính (PO reads each story and its AC) | [5 empty] | 2 | Nguyễn Minh Chính | Product Owner + Developer · Sprint Leader S2
US ID | Item | Round 1 (cards: Đạt, Chính) | Round 2 | Round 3 | Final SP | Reasoning that led to agreement / notes
US-01 | Customer registers with email and password; hashed password; client + server validation
US-02 | User logs in and logs out
US-03 | Administrator creates and locks accounts; roles Administrator / Customer; admin functions blocked on the server
NFR-02 | Release hosted on a free server, reachable by the lecturer, online until 17/11
US-08 | Administrator adds a book: title, author, category, price > 0, description, cover image, stock
US-09 | Administrator edits book information
US-10 | Administrator deletes a book = hidden, no hard delete
US-24 | Administrator manages categories
US-25 | Administrator manages authors
US-05 | Customer browses a card grid (cover, title, author, price), 12 per page, newest first
NFR-01 | ≥ 30 sample books; list page loads in < 2 s
US-21 | Responsive, cross-browser layout (desktop, tablet, phone)
US-07 | Book details page; unknown ID → friendly message; Back returns to the same list page
US-06 | Search by title or author; filter by category and price range; works with pagination
US-26 | CR-06: Store Staff role and permissions
US-27 | CR-06: book shows 'Last updated by … at …'
Questions the team asked the Product Owner (record at least 3) – proposed below; keep only those really asked and write the PO's answer
# | Question | PO answer
1 | US-02: are password reset and account lockout part of Release 1.0, or only log in / log out?
2 | US-08: is ISBN required for a book in Release 1.0 (F2 lists title, author, category, price, description, cover, stock)?
3 | NFR-01: is the < 2 s list load measured on a warm server, or must it also hold after a free-hosting cold start?
4 | US-03: can an Administrator lock another Administrator, and what does a locked user see when logging in?