# Sprint 1 Report – Team 6 Page Turners

Table of Contents

# Sprint 1 Report – Plan baseline & F1

| Item | Value |
| --- | --- |
| Team | Team 6 "Page Turners" |
| Sprint | S1, 23/10 – 29/10/2026 |
| Sprint Leader | Hồ Du Tuấn Đạt |
| Product Owner | Nguyễn Minh Chính |
| Repository | https://github.com/Tdat10052499/E-Commercial-Book-Store |
| Jira board | TBD |
| Hosted URL | TBD |

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | First report. Actual hours, burndown, Daily log and Retro content to be filled by the team |

## Status summary (Green / Amber / Red)

| Area | Status | Evidence |
| --- | --- | --- |
| Scope | Amber | F1 implemented and passing local automated tests (21/24 ACs); NFR-03 hosting not yet deployed |
| Schedule | Red | Sprint 1 artefacts not complete at 29/10 23:59 (issue I-01) |
| Cost | TBD | Actual hours not yet exported from Jira |
| Quality | Green | 16/16 unit/integration tests, 18/18 e2e checks pass locally; 0 open defects |

## Contents

- Sprint Planning – S1_Backlog (Sprint Goal, capacity, items, tasks)

- Daily log

- Test cases F1 with results

- Review and Retrospective

# Sprint 1 Backlog (S1_Backlog)

Sprint: S1 – Plan baseline & F1 · 23/10 – 29/10/2026 · Leader: Hồ Du Tuấn Đạt · PO: Nguyễn Minh Chính

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0 (TA) | 15/10/2026 | Team 6 | 2-week Sprint, 6 stories / 22 SP, 68 h plan [04 §5] |
| 1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Re-planned to 1-week S1 = F1 + PM baseline only [05 #11]. Task hours are proposals; Jira Original Estimate must match after the team confirms |

## Sprint Goal (measurable)

By 29/10/2026, on the hosted URL: a visitor can register and log in/out; an administrator can create accounts with a role and lock/unlock them; a non-admin gets 403 on every /admin URL; passwords are stored as bcrypt hashes — verified by 24 F1 test cases (one per AC) all passing. In parallel, PMP v1.0, Product Backlog v1.0, Release Plan/BAC and the CR-06 Change Log entry are baselined.

## Capacity

| Member | Available days | Focus h/day | Capacity (h) |
| --- | --- | --- | --- |
| Hồ Du Tuấn Đạt | 5 | 4 | 20 (plan) |
| Nguyễn Minh Chính | 5 | 4 | 20 (plan) |
| Total |  |  | 40 (plan) – plan/INPUTS.md §2, PO 30/10/2026 |

## Selected items

US-01 (3), US-02 (3), US-03 (5), US-04 (3), NFR-01 (2), NFR-03 (2) = 18 SP → planned velocity S1 = 18 SP (PO estimates, planning-poker-log.md v1.1). Actual velocity = SP of these items that meet the DoD at Review 1.

## Tasks (each ≤ 1 person-day = 8 h)

| Task | Item | Description | Owner | Est. h (plan) | Actual h (Jira) | Status |
| --- | --- | --- | --- | --- | --- | --- |
| S1-T01 | PM | Product Backlog v1.0 + DoR (GWT ACs) | Chính | 4 | TBD | TBD |
| S1-T02 | PM | Planning Poker session + Release Plan + BAC | Chính | 2 | TBD | TBD |
| S1-T03 | PM | PMP v1.0 parts 1, 3, 5, 6 | Đạt | 6 | TBD | TBD |
| S1-T04 | PM | PMP v1.0 parts 2, 4, 7 | Chính | 4 | TBD | TBD |
| S1-T05 | CR-06 | Change Log entry + impact analysis + CCB options | Chính | 3 | TBD | TBD |
| S1-T06 | NFR-03 | Scaffold app, DB schema, deploy skeleton | Đạt | 4 | TBD | TBD |
| S1-T07 | US-01, NFR-01 | Register (form, client + server validation, bcrypt) | Đạt | 4 | TBD | TBD |
| S1-T08 | US-02 | Login/logout, sessions, locked-account check | Đạt | 3 | TBD | TBD |
| S1-T09 | US-03 | Admin account list, create account with role, lock/unlock | Chính | 5 | TBD | TBD |
| S1-T10 | US-04 | Server-side role guard, 403 page, hide admin menu | Đạt | 2 | TBD | TBD |
| S1-T11 | NFR-04 (base) | Responsive base layout and styles | Chính | 3 | TBD | TBD |
| S1-T12 | Test | F1 test cases (24) + automated tests + run | Chính | 3 | TBD | TBD |
| S1-T13 | PM | Workbook c2, Sprint Report c3, submission | Đạt | 3 | TBD | TBD |
| S1-T14 | PM | Review/Retro 1 preparation | Đạt | 2 | TBD | TBD |
|  |  | Total (plan) | Đạt 24 · Chính 24 | 48 | TBD |  |

Check against capacity: 48 h (plan) exceeds the 40 h capacity by 8 h (20 %). PO note (30/10/2026): Sprint 1 had already ended when capacity was confirmed, so the overload is recorded, not hidden: it is one cause of issue I-01 (late Sprint 1 artefacts). Lesson for Sprint Planning 2: select work only up to 40 h.

# Sprint 1 – Daily Scrum Log

Timebox ≤ 10 min; asynchronous allowed but must be logged [03 §4.2]. Channel: TBD. Only real entries from the team are recorded here; AI does not invent past stand-ups. If no stand-up happened on a day, write "No Daily held" and explain in Retro.

| Date | Member | Yesterday | Today | Blockers | Hours logged in Jira |
| --- | --- | --- | --- | --- | --- |
| Fri 23/10 | Đạt | TBD | TBD | TBD | TBD |
| Fri 23/10 | Chính | TBD | TBD | TBD | TBD |
| Mon 26/10 | Đạt | TBD | TBD | TBD | TBD |
| Mon 26/10 | Chính | TBD | TBD | TBD | TBD |
| Tue 27/10 | Đạt | TBD | TBD | TBD | TBD |
| Tue 27/10 | Chính | TBD | TBD | TBD | TBD |
| Wed 28/10 | Đạt | TBD | TBD | TBD | TBD |
| Wed 28/10 | Chính | TBD | TBD | TBD | TBD |
| Thu 29/10 | Đạt | TBD | TBD | TBD | TBD |
| Thu 29/10 | Chính | TBD | TBD | TBD | TBD |

# Sprint 1 – Test Cases F1

Format: GWT → steps → expected → actual [03 §6.1-7]. One test case per AC (24 ACs → 24 test cases).

## Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Test cases from F1 ACs; automated results from a real local run |
| 1.1 | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Manual run found defect DEF-F1-01 (TC-F1-15); expected result made precise; E2E assertion tightened |

Evidence of automated run (local build, PostgreSQL 16, 30/10/2026): npm test → 16/16 pass (UNIT = tests/validation.test.js, INT = tests/users.test.js); npm run e2e → 18/18 pass (E2E = app/e2e/f1.e2e.js, Chromium). Log: pm/sprints/S1/evidence/test-run-2026-10-30.txt. Manual run on the hosted URL must be done by a team member before the Review and written in the last column (Pass/Fail, date, tester).

| TC | AC | Given | When (steps) | Then (expected) | Automated | Actual – local automated | Actual – hosted, manual |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TC-F1-01 | US-01/AC-01 | Register page open | Submit valid name, new email, password Reader2026 | Account created as Customer, signed in, redirected home | E2E + INT | Pass (30/10) | TBD |
| TC-F1-02 | US-01/AC-02 | Customer x@y.com exists | Register with X@Y.COM | "Email is already registered" by email field; no new account | E2E + INT | Pass (30/10) | TBD |
| TC-F1-03 | US-01/AC-03 | Register page open | Submit not-an-email; then empty fields; then POST bypassing client | Field errors on client; server also rejects | E2E + INT | Pass (30/10) | TBD |
| TC-F1-04 | US-01/AC-04 | Register page open | Password abc1234 (7) then abcd1234 (8) | 7 rejected, 8 accepted | E2E + UNIT | Pass (30/10) | TBD |
| TC-F1-05 | US-02/AC-01 | Active account | Log in with correct credentials | Signed in; name and Log out shown | E2E + INT | Pass (30/10) | TBD |
| TC-F1-06 | US-02/AC-02 | Active account | Log in with wrong password; with unknown email | Same generic "Invalid email or password" | E2E + INT | Pass (30/10) | TBD |
| TC-F1-07 | US-02/AC-03 | Account locked by admin | Log in with correct credentials | "This account is locked…" | E2E + INT | Pass (30/10) | TBD |
| TC-F1-08 | US-02/AC-04 | Signed in | Click Log out; open /admin | Session ended; redirected to Login | E2E | Pass (30/10) | TBD |
| TC-F1-09 | US-02/AC-05 | Account e@x.com | Log in with E@X.COM | Signed in | E2E + INT + UNIT | Pass (30/10) | TBD |
| TC-F1-10 | US-03/AC-01 | Signed in as admin | Create account with role Customer | Appears in list, role Customer, Active | E2E + INT | Pass (30/10) | TBD |
| TC-F1-11 | US-03/AC-02 | Admin; another active account | Lock, then Unlock | Locked user cannot log in; after unlock can | E2E + INT | Pass (30/10) | TBD |
| TC-F1-12 | US-03/AC-03 | Signed in as admin | Click Lock on own row | "You cannot lock your own account" | E2E + INT | Pass (30/10) | TBD |
| TC-F1-13 | US-03/AC-04 | Admin; email exists | Create account with that email | Field error; no account | E2E + INT | Pass (30/10) | TBD |
| TC-F1-14 | US-03/AC-05 | User signed in in another browser | Admin locks that user; user reloads | User is signed out | E2E + INT | Pass (30/10) | TBD |
| TC-F1-15 | US-04/AC-01 | Not signed in | Open /admin/accounts | Redirect to /login?next=%2Fadmin%2Faccounts; after login back on that page | E2E | Pass (30/10) | TBD |
| TC-F1-16 | US-04/AC-02 | Signed in as Customer | Open /admin/accounts directly | HTTP 403 "Access denied" | E2E | Pass (30/10) | TBD |
| TC-F1-17 | US-04/AC-03 | Signed in as admin | Open /admin | Admin dashboard shown | E2E | Pass (30/10) | TBD |
| TC-F1-18 | US-04/AC-04 | Signed in as Customer | Look at header on any page | No Admin menu | E2E | Pass (30/10) | TBD |
| TC-F1-19 | NFR-01/AC-01 | New account saved | Inspect users.password_hash in DB | bcrypt hash $2…$10$…, not plain text | INT | Pass (30/10) | TBD |
| TC-F1-20 | NFR-01/AC-02 | Any form | Send invalid data bypassing client | Server rejects, nothing stored | INT | Pass (30/10) | TBD |
| TC-F1-21 | NFR-01/AC-03 | Register form | Name 101 chars; password 65 chars | Rejected (100 / 64 accepted) | UNIT | Pass (30/10) | TBD |
| TC-F1-22 | NFR-03/AC-01 | develop deployed | Open public URL | Home page over HTTPS | — | Not run (needs hosting) | TBD |
| TC-F1-23 | NFR-03/AC-02 | Site idle ≥ 15 min | Open URL | Responds; URL recorded | — | Not run (needs hosting) | TBD |
| TC-F1-24 | NFR-03/AC-03 | 17/11/2026 | Open URL | Online | — | Not run (needs hosting) | TBD |

## Defects found

| ID | TC | Found | Description | Fix | Status |
| --- | --- | --- | --- | --- | --- |
| DEF-F1-01 | TC-F1-15 | 30/10/2026, manual run (Đạt) | Any admin URL redirected to /login?next=%2Fadmin: the admin layout guard used a fixed default path, so after login the user landed on the dashboard instead of the page requested. The automated check only tested for next= and missed it | src/middleware.js passes the requested path; requireAdmin uses it; E2E now asserts the exact next | Fixed, re-verified locally (curl); manual re-test TBD |

## Summary (local automated)

| ACs | Test cases | Executed | Pass | Fail | Not run |
| --- | --- | --- | --- | --- | --- |
| 24 | 24 | 21 | 21 | 0 | 3 (NFR-03 hosting) |

# Sprint 1 – Review & Retrospective (Fri 30/10/2026)

Presenter: Sprint Leader S1. Structure follows [03 §8]. Fill the TBD cells with real data before class.

## 1. Sprint Goal and result

- Goal: see sprint-backlog.md.

- Result: TBD (Met / Partly met / Not met) – items Done vs committed: TBD.

## 2. Demo against ACs (F1)

Script (on the hosted URL or local run if hosting is not ready):

- Register a new customer (US-01/AC-01) → try the same email again (AC-02) → try a 7-char password (AC-04).

- Log out, log in with wrong password (US-02/AC-02), then correct one (AC-01).

- Log in as admin → create an account (US-03/AC-01) → lock it (AC-02) → try logging in as that user (US-02/AC-03) → try to lock own account (US-03/AC-03).

- As a customer, open /admin directly → 403 (US-04/AC-02); logged out → redirect to login (AC-01).

- Show password hash in the database (NFR-01/AC-01).

## 3. Burndown

TBD – export from Jira; explain flat or rising segments.

## 4. Planned vs actual hours

|  | Plan (h) | Actual (h, Jira Completed Work) |
| --- | --- | --- |
| Đạt | 24 (proposal) | TBD |
| Chính | 24 (proposal) | TBD |
| Total | 48 | TBD |

## 5. Risks and issues

Top risks R01, R03, R05 (PMP-5); issue I-01 (late S1 artefacts).

## 6. CR-06 (CCB in the same session)

Present options A/B/C from pm/change/CR-06-impact-analysis.md; record Sponsor decision and reason.

## 7. Retrospective

| Went well | To improve |
| --- | --- |
| TBD (team) | TBD (team) |

Proposed action items (team to confirm; tracked in S2): | # | Action | Owner | Due | Measure | |---|---|---|---|---| | A1 | Daily Scrum logged every working day before 22:00 | Leader S2 | each day of S2 | 5/5 entries per member | | A2 | Draft Sprint files by Wednesday 20:00, submit Thursday before 21:00 | Leader S2 | 04/11 | Submission timestamp < 23:59 | | A3 | Log Completed Work in Jira the same day a task moves | Both | daily | 100 % of Done tasks have hours |

## 8. Plan for Sprint 2

F2 + F3 (+ CR-06 per CCB); Planning 2 uses actual S1 velocity [03 §6.2].