## ProductBacklog
Source: pm/backlog/product-backlog.md
Values marked TBD need team input (plan/INPUTS.md). Plan figures are not actuals.
Summary
Group | Items | SP (plan)
Release 1.0 – Must | 18 (US-01…US-13, NFR-01…NFR-05) | TBD after Planning Poker
CR-06 – pending CCB 30/10 | 2 (US-24, US-25) | TBD
Won't (this release) | 10 | not estimated for R1.0 (v0 SP kept for reference)
Total items | 30 | PSP = TBD
A. Release 1.0 items
Rank | ID | v0 ID | F | User story | SP | MoSCoW | Sprint (plan)
1 | US-01 | US-01 | F1 | As a visitor, I want to register with my name, email and password so that I can sign in as a customer. | TBD | Must | S1
2 | US-02 | US-02 | F1 | As a registered user, I want to log in and log out so that only I can use my account. | TBD | Must | S1
3 | US-03 | US-03 | F1 | As an administrator, I want to create accounts with a role and lock/unlock accounts so that I control who can use the system. | TBD | Must | S1
4 | US-04 | new | F1 | As the store owner, I want admin functions to be blocked for anyone who is not an administrator so that catalogue and account data stay safe. | TBD | Must | S1
5 | NFR-01 | new | F1 | As the store owner, I want passwords stored as hashes and every form validated on client and server so that customer data is protected. | TBD | Must | S1
6 | NFR-03 | new | All | As the customer (Ms. Le), I want the site hosted on a free public URL until 17/11/2026 so that I can review each increment. | TBD | Must | S1
7 | US-05 | US-08 | F2 | As an administrator, I want to add a book (title, author, category, price, description, cover image, stock) so that it appears in the catalogue. | TBD | Must | S2
8 | US-06 | US-09 | F2 | As an administrator, I want to edit a book's information so that the catalogue stays correct. | TBD | Must | S2
9 | US-07 | US-10 | F2 | As an administrator, I want to delete (hide) a book without losing its record so that discontinued books disappear from the shop. | TBD | Must | S2
10 | US-08 | new | F2 | As an administrator, I want to add, rename and remove categories so that books can be grouped. | TBD | Must | S2
11 | US-09 | new | F2 | As an administrator, I want to add, edit and remove authors so that books reference consistent author data. | TBD | Must | S2
12 | NFR-02 | (T-16) | F2/F3 | As the customer (Ms. Le), I want at least 30 sample books loaded so that the catalogue can be demonstrated and performance measured. | TBD | Must | S2
13 | US-10 | US-05 | F3 | As a customer, I want to browse books in a grid of 12 per page, newest first, so that I can see what is new. | TBD | Must | S2
14 | NFR-04 | US-21 | F3 | As a customer, I want every page to work on phone, tablet and desktop so that I can shop from any device. | TBD | Must | S2
15 | US-11 | US-07 | F4 | As a customer, I want to open a book's detail page and go back to the same list page so that I can compare books without losing my place. | TBD | Must | S3
16 | US-12 | US-06 | F5 | As a customer, I want to search by title or author so that I can find a specific book quickly. | TBD | Must | S3
17 | US-13 | US-06 | F5 | As a customer, I want to filter by category and price range together with search and pagination so that I only see relevant books. | TBD | Must | S3
18 | NFR-05 | (US-06 AC) | F3/F5 | As a customer, I want the book list to load in under 2 seconds so that browsing feels fast. | TBD | Must | S3
B. CR-06 items (pending CCB on 30/10/2026 – not in baseline until approved)
ID | F | User story | SP | MoSCoW | Sprint
US-24 | F1, F2 | As a store staff member, I want to add and edit books and manage categories and authors, without deleting books or managing accounts, so that I can update the catalogue daily without full admin rights. [CR-06 §1] | TBD | Must (if approved) | per CCB option
US-25 | F2 | As an administrator, I want each book to show "Last updated by <name> at <time>" so that I know who changed it. [CR-06 §1] | TBD | Must (if approved) | per CCB option
C. Won't (this release) – kept for Release 2
ID | v0 ID | Story (short) | v0 SP | Reason
R2-01 | US-04 | Customer profile and shipping addresses | 2 | Supports checkout, out of scope [03 §2.2]
R2-02 | US-11 | Shopping cart | 5 | Cart out of scope [03 §2.2]
R2-03 | US-12 | Checkout & online payment | 8 | Payment out of scope
R2-04 | US-13 | Order history & tracking | 3 | Depends on checkout
R2-05 | US-14 | Staff processes orders | 5 | Depends on checkout
R2-06 | US-15/16 | Promotions and discount codes | 5 + 3 | Depends on checkout
R2-07 | US-17/18 | Multi-store inventory and in-store pickup | 8 + 5 | Not in F1–F5
R2-08 | US-19 | Ratings & reviews | 5 | Not in F1–F5
R2-09 | US-20 | Wishlist | 2 | Not in F1–F5
R2-10 | US-22, US-23, US-02 (reset) | Brand style guide, recommendations, password reset by email | 3 + 8 + – | Not in F1–F5; SMTP risk on free hosting [05 #7]

## DoR
Source: pm/backlog/definition-of-ready.md
Version history
Version | Date | Author | Change
1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | New; the TA baseline had no DoR [05 #15]
Version history
# | Check | Evidence
DoR-1 | Written as *As a… I want… so that…* and satisfies INVEST | Product Backlog row
DoR-2 | ACs in Given–When–Then, numbered US-xx/AC-0n, covering main, exception and boundary flows | Section D of the backlog
DoR-3 | Estimated in Fibonacci SP by Planning Poker; ≤ 13 SP (otherwise split) | Planning Poker log
DoR-4 | MoSCoW priority set and ranked by the PO | Backlog rank
DoR-5 | Dependencies identified (e.g. F3 needs F2 data) and none blocking | Backlog notes
DoR-6 | Within Release 1.0 scope (not cart/payment/social login) or approved by CCB | [03 §2.2], Change Log
DoR-7 | Testable: each AC can be turned into ≥ 1 test case | Test case file

## PlanningPoker
Source: pm/backlog/planning-poker-log.md
Votes are entered by the team only. Attach photos of each reveal.
Version history
Version | Date | Author | Change
1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Log table prepared. Votes must be entered by the team; none are filled in by AI.
Session 1 – Release 1.0 baseline (date: TBD, place/tool: TBD, facilitator: PO)
Item | Round | Đạt | Chính | Highest/lowest reasoning | Result SP
US-01 Register | 1 | TBD | TBD |  | TBD
US-02 Log in/out | 1 | TBD | TBD |  | TBD
US-03 Admin creates & locks accounts | 1 | TBD | TBD |  | TBD
US-04 Server-side access control | 1 | TBD | TBD |  | TBD
NFR-01 Hashing & validation | 1 | TBD | TBD |  | TBD
NFR-03 Hosting | 1 | TBD | TBD |  | TBD
US-05 Add book | 1 | TBD | TBD |  | TBD
US-06 Edit book | 1 | TBD | TBD |  | TBD
US-07 Hide book | 1 | TBD | TBD |  | TBD
US-08 Manage categories | 1 | TBD | TBD |  | TBD
US-09 Manage authors | 1 | TBD | TBD |  | TBD
NFR-02 Seed ≥ 30 books | 1 | TBD | TBD |  | TBD
US-10 Book grid | 1 | TBD | TBD |  | TBD
NFR-04 Responsive UI | 1 | TBD | TBD |  | TBD
US-11 Book detail | 1 | TBD | TBD |  | TBD
US-12 Search | 1 | TBD | TBD |  | TBD
US-13 Filter + pagination | 1 | TBD | TBD |  | TBD
NFR-05 Performance < 2 s | 1 | TBD | TBD |  | TBD
Session 2 – CR-06 impact estimate (before CCB 30/10)
Item | Round | Đạt | Chính | Reasoning | Result SP
US-24 Store Staff role | 1 | TBD | TBD |  | TBD
US-25 Last-updated audit | 1 | TBD | TBD |  | TBD
Rework/regression of F1 (US-03, US-04) | 1 | TBD | TBD |  | TBD

## ReleasePlan
Source: pm/pmp/03-master-release-plan.md
Values marked TBD need team input (plan/INPUTS.md). Plan figures are not actuals.
Version history
Version | Date | Author | Change
0.1 (TA) | 15/10/2026 | Team 6 | Team Assignment release planning: velocity assumed 22 SP per 2-week Sprint; Must + Should = 79 SP over ~4 Sprints [04 §4]
1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Rebaselined to the Final Project brief: 3 one-week Sprints, scope F1–F5 only, cart/payment/social login out of scope [03 §2.2, §5]; capacity-based velocity; BAC formula at 200,000 VND/h; CR-06 recorded as pending CCB
3.2 Milestones (fixed by the brief)
# | Milestone | Date / time (GMT+7) | Evidence | Source
M0 | Project start, brief issued | Fri 23/10 | – | [03 §5]
M1 | CR-06 issued by Sponsor | Tue 27/10 | CR-06 in Change Log | [CR-06]
M2 | Sprint 1 submission (c1, c2, c3, c0) | Thu 29/10 23:59 | eLearning upload | [03 §7]
M3 | Review/Retro 1 + CCB for CR-06 | Fri 30/10 | Review slides, CCB decision | [03 §5], [CR-06 §5]
M4 | Baseline v1.0 tagged (baseline-v1.0) | Fri 30/10 | Git tag | PMP-6
M5 | Sprint 2 submission (c2, c3, c4 CR, c0) | Thu 05/11 23:59 | eLearning upload | [03 §7]
M6 | Review/Retro 2 | Fri 06/11 | Review slides | [03 §5]
M7 | Release v1.0 tagged + release notes | Thu 12/11 | Git tag, notes | [03 §6.3]
M8 | Sprint 3 submission (c2, c3, c5 UAT, c0) | Thu 12/11 23:59 | eLearning upload | [03 §7]
M9 | Review 3 + UAT with customer | Fri 13/11 | Signed UAT minutes | [03 §6.3]
M10 | Final submission (c1 Final, c2 Final, c6 Report, c6 Slides, Eval360) | Sun 15/11 23:59 | eLearning upload | [03 §7]
M11 | Final presentation; site online until end of day | Tue 17/11 07:00 | Live demo | [03 §8]
3.3 Sprint plan and leader rotation
Sprint | Dates | Leader | Sprint Goal (plan) | Increment | PM focus (rubric S4)
S1 – Plan baseline & F1 | 23/10 – 29/10 | Hồ Du Tuấn Đạt *(to confirm)* | "Users can register, log in and log out; an administrator can create and lock accounts; non-admins are blocked from admin functions on the server." | F1 | PMP v1.0
S2 – Execution, monitoring & change | 30/10 – 05/11 | Nguyễn Minh Chính (PO) *(to confirm)* | "Admins manage books, categories and authors (soft delete), and customers browse 12 books per page, newest first, on any device." (+ CR-06 if approved) | F2, F3 (+CR-06) | CR + risk/issue
S3 – Complete & acceptance | 06/11 – 12/11 | Hồ Du Tuấn Đạt *(to confirm)* | "Customers open book details and search/filter by title, author, category and price range together with pagination; Release v1.0 passes UAT." | F4, F5 | UAT + Release
Closure | 13/11 – 17/11 | Both | Final Report, EVM, Lessons Learned, slides, video | Release 1.0 online | –
3.4 Allocation of backlog items to Sprints (plan)
Sprint | Items | SP (plan)
S1 | US-01 Register · US-02 Log in/out · US-03 Admin creates & locks accounts · US-04 Server-side role guard · NFR-01 Password hashing & validation · NFR-03 Hosting/deploy skeleton | TBD
S2 | US-05 Add book · US-06 Edit book · US-07 Hide (soft delete) book · US-08 Manage categories · US-09 Manage authors · NFR-02 Seed ≥30 books · US-10 Book grid 12/page newest first · NFR-04 Responsive UI | TBD
S2 (if CR-06 approved, option per CCB) | US-24 Store Staff role & permissions · US-25 "Last updated by" audit | TBD
S3 | US-11 Book detail page (+friendly not-found, Back keeps page) · US-12 Search by title/author · US-13 Filter by category & price range with pagination · NFR-05 List page < 2 s | TBD
Release 1.0 total |  | PSP = TBD
3.5 Capacity and expected velocity
Sprint | Đạt (h) | Chính (h) | Capacity (h) | Source
S1 | TBD | TBD | TBD | plan/INPUTS.md §2
S2 | TBD | TBD | TBD
S3 | TBD | TBD | TBD
3.7 Master schedule (work packages by date)
Phase | Work package | Start | Due | Owner | Depends on
Sprint 1 (23–29/10)
P00 | Repo, branches, access (GV invited) | 27/10 | 27/10 | Đạt | –
P01 | Kick-off, roles, working agreement, capacity | 27/10 | 28/10 | Both | P00
P02 | Product Backlog v1.0 (GWT, DoR) | 27/10 | 28/10 | PO | P01
P03 | Planning Poker, Release Plan, BAC | 28/10 | 28/10 | PO + Leader | P02
P04 | Stack, scaffold, deploy skeleton | 27/10 | 28/10 | Đạt | P01
P05 | Sprint Planning 1 → Jira | 28/10 | 28/10 | Leader | P03
P06–P07 | Build F1; F1 test cases | 28/10 | 29/10 | Both | P04, P05
P08 | PMP v1.0 (7 parts) | 27/10 | 29/10 | Leader + PO | P01, P03
P09 | CR-06 Change Log, impact analysis, options | 28/10 | 29/10 | PO | P03
P10 | Daily log, burndown, actual hours | 23/10 | 29/10 | Leader | continuous
P11 | Package & submit S1 | 29/10 | 29/10 23:59 | Leader | above
P12 | Review/Retro 1 + CCB | 30/10 | 30/10 | Leader + PO | P11
Sprint 2 (30/10–05/11)
P13 | Sprint Planning 2 (actual velocity S1) | 30/10 | 30/10 | Leader | P12
P14 | Update baseline per CCB, tag | 30/10 | 31/10 | PO | CCB decision
P15 | Build F2 (+ seed ≥30 books) | 31/10 | 03/11 | Both | P13
P16 | Build F3 | 02/11 | 04/11 | Both | P15
P17 | Build CR-06 (if approved) | 01/11 | 04/11 | Both | P14
P18 | Test cases F2, F3, CR-06 + regression F1 | 03/11 | 05/11 | Both | P15–P17
P19 | Weekly Status, risk & issue log | 30/10 | 05/11 | Leader | continuous
P20 | c4 Change Request form | 31/10 | 05/11 | PO | P14
P21 | Package & submit S2 | 05/11 | 05/11 23:59 | Leader | above
P22 | Review/Retro 2 | 06/11 | 06/11 | Leader | P21
Sprint 3 (06–12/11)
P23 | Sprint Planning 3 (actual velocity S2) | 06/11 | 06/11 | Leader | P22
P24–P25 | Build F4, F5 | 07/11 | 10/11 | Both | P23
P26 | Tests F4, F5, regression F1–F3, performance | 10/11 | 11/11 | Both | P24, P25
P27 | Release v1.0: merge to main, tag, notes | 11/11 | 12/11 | Leader | P26
P28 | UAT script (all ACs) | 10/11 | 12/11 | PO | P26
P29 | Monitoring + draft EVM | 06/11 | 12/11 | Leader | continuous
P30 | Package & submit S3 | 12/11 | 12/11 23:59 | Leader | above
P31 | Review 3 + UAT + minutes | 13/11 | 13/11 | Leader + PO | P30
Closure (13–17/11)
P32 | Final hosting, demo accounts, closure data | 13/11 | 14/11 | Đạt | P31
P33 | Final Report, EVM, Lessons Learned, PMP/Workbook Final | 13/11 | 15/11 | Both | P31, P32
P34 | Slides + demo video ≤ 3 min | 14/11 | 15/11 | Both | P33
P35 | Final submission + Eval360 each | 15/11 | 15/11 23:59 | Both | P33, P34
P36 | Final presentation | 16/11 | 17/11 07:00 | Both | P35
3.8 Baseline and change history of this plan
Baseline | Date | Trigger | PSP | BAC | Tag
Baseline v1.0 | 30/10/2026 | Sprint 1 submission | TBD | TBD | baseline-v1.0
Rebaseline v1.1 | TBD | CCB decision on CR-06 (if Approve) | TBD | TBD | baseline-v1.1

## S1_Backlog
Source: pm/sprints/S1/sprint-backlog.md
Values marked TBD need team input (plan/INPUTS.md). Plan figures are not actuals.
Version history
Version | Date | Author | Change
0 (TA) | 15/10/2026 | Team 6 | 2-week Sprint, 6 stories / 22 SP, 68 h plan [04 §5]
1.0-draft | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Re-planned to 1-week S1 = F1 + PM baseline only [05 #11]. Task hours are proposals; Jira Original Estimate must match after the team confirms
Capacity
Member | Available days | Focus h/day | Capacity (h)
Hồ Du Tuấn Đạt | TBD | TBD | TBD
Nguyễn Minh Chính | TBD | TBD | TBD
Total |  |  | TBD (scenario 40 h, PMP-3 §3.5)
Tasks (each ≤ 1 person-day = 8 h)
Task | Item | Description | Owner | Est. h (plan) | Actual h (Jira) | Status
S1-T01 | PM | Product Backlog v1.0 + DoR (GWT ACs) | Chính | 4 | TBD | TBD
S1-T02 | PM | Planning Poker session + Release Plan + BAC | Chính | 2 | TBD | TBD
S1-T03 | PM | PMP v1.0 parts 1, 3, 5, 6 | Đạt | 6 | TBD | TBD
S1-T04 | PM | PMP v1.0 parts 2, 4, 7 | Chính | 4 | TBD | TBD
S1-T05 | CR-06 | Change Log entry + impact analysis + CCB options | Chính | 3 | TBD | TBD
S1-T06 | NFR-03 | Scaffold app, DB schema, deploy skeleton | Đạt | 4 | TBD | TBD
S1-T07 | US-01, NFR-01 | Register (form, client + server validation, bcrypt) | Đạt | 4 | TBD | TBD
S1-T08 | US-02 | Login/logout, sessions, locked-account check | Đạt | 3 | TBD | TBD
S1-T09 | US-03 | Admin account list, create account with role, lock/unlock | Chính | 5 | TBD | TBD
S1-T10 | US-04 | Server-side role guard, 403 page, hide admin menu | Đạt | 2 | TBD | TBD
S1-T11 | NFR-04 (base) | Responsive base layout and styles | Chính | 3 | TBD | TBD
S1-T12 | Test | F1 test cases (24) + automated tests + run | Chính | 3 | TBD | TBD
S1-T13 | PM | Workbook c2, Sprint Report c3, submission | Đạt | 3 | TBD | TBD
S1-T14 | PM | Review/Retro 1 preparation | Đạt | 2 | TBD | TBD
|  | Total (plan) | Đạt 24 · Chính 24 | 48 | TBD

## Burndown
Day | Date | Ideal remaining (h, plan) | Actual remaining (h, Jira)
1 | Fri 23/10 | 38.4 | TBD
2 | Mon 26/10 | 28.8 | TBD
3 | Tue 27/10 | 19.2 | TBD
4 | Wed 28/10 | 9.6 | TBD
5 | Thu 29/10 | 0 | TBD
Ideal line uses the proposed 48 h; actual values must come from Jira Completed Work.

## RiskRegister
Source: pm/pmp/05-risk-plan.md
5.2 Risk register v1.0 (status at 30/10/2026)
ID | Risk (cause → event → effect) | Cat. | P | I | P×I | Strategy & response | Owner | Trigger | Status
R01 | Only 2 members must deliver F1–F5 plus heavy PM documentation → workload exceeds capacity → items slip | Resource | 4 | 4 | 16 | Mitigate: tasks ≤ 1 person-day, capacity-based plan, AI-assisted drafting with review | Leader | Burndown flat for 2 days | Occurred → I-01
R02 | Lab 1/Lab 2/TA week 2 not submitted → PMP must be written from scratch → S1 late | Schedule | 5 | 3 | 15 | Mitigate: reuse TA files, draft PMP early | Leader S1 | PMP not ready 24 h before deadline | Occurred → I-01
R03 | Free host sleeps (cold start) → list page > 2 s or lecturer cannot open site | Technical | 3 | 4 | 12 | Mitigate: pick host without long sleep or add keep-alive ping; measure warm & cold | Đạt | First load > 5 s | Open
R04 | Jira Free lacks time tracking fields → no actual hours → EVM AC invalid | Tool | 2 | 5 | 10 | Mitigate: verify in S1; fallback: hours sheet in Workbook | Leader | Fields missing on issue | Open
R05 | CR-06 approved → extra scope and F1 rework → S2 overloaded | Scope | 4 | 3 | 12 | Mitigate: ≥ 2 options at CCB incl. phased delivery; rebaseline PSP/BAC | PO | CCB Approve | Open
R06 | Planning Poker evidence or regular commits missing → B4, S5 and individual factor reduced | Quality/Process | 3 | 4 | 12 | Avoid: photo of each reveal; commit at least daily per member | Both | No commit by a member in 2 days | Open
R07 | eLearning dates differ from the brief → wrong item or time used for upload | Schedule | 3 | 3 | 9 | Mitigate: ask lecturer; submit by brief date | Leader | Upload slot not found | Open
R08 | Security defect (plain passwords, missing server-side role check) → AC/NFR fail at UAT | Quality | 2 | 5 | 10 | Avoid: bcrypt, server guards, permission tests | Đạt | Test fails | Open
R09 | A member is sick or busy with other exams → capacity drops | Resource | 3 | 3 | 9 | Mitigate: shared knowledge via PR reviews; buffer in S3 | Leader | Member reports unavailability | Open
R10 | Integration of F3/F4/F5 (pagination + search + Back) breaks state → F4/F5 ACs fail | Technical | 3 | 3 | 9 | Mitigate: keep page/filter in URL query from S2 | Chính | Back loses page in test | Open

## IssueLog
Source: pm/pmp/05-risk-plan.md
5.3 Issue Log (risks that occurred)
ID | From risk | Date | Description | Impact | Action | Owner | Status
I-01 | R01, R02 | 30/10/2026 | Sprint 1 artefacts not completed in the repository by 29/10 23:59 | Possible late penalty (−10 % / 5 h); less time for F1 | Catch-up night 29–30/10 with AI-assisted drafting; record submission time; discuss in Retro 1 | Leader S1 | Open

## ChangeLog
Source: pm/change/change-log.md
Version history
Version | Date | Author | Change
1.0 | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | CR-06 recorded (due 29/10 23:59 per [CR-06 §5]; entry time to be stated honestly in the submission)
Version history
CR ID | Date received | Requester | Title | Affected | Customer priority | Description | Impact summary (plan) | Options | CCB date | Decision | Reason | Baseline updated | Status
CR-06 | 27/10/2026 | Ms. Le (Sponsor) | Add a Store Staff role | F1, F2 | High | Third role *Store Staff*: add/edit books, manage categories and authors; cannot delete books or access account management; admin assigns roles. Each book stores and shows "Last updated by <name> at <time>" on the book admin page [CR-06 §1] | +2 items (US-24, US-25) + rework of US-03/US-04; ≈ 12 h (plan) ≈ 2.4 M VND; SP TBD (Planning Poker) – see CR-06-impact-analysis.md | A full in S2 · B phased S2/S3 · C defer to R2 | 30/10/2026 | TBD (Sponsor) | TBD | TBD | Analysed – awaiting CCB

## ConfigItems
Source: pm/pmp/06-configuration-management.md
6.1 Configuration items (CI)
CI-ID | Item | Type | Location | Owner | Baseline
CI-01 | Project Management Plan (7 parts) | Document | pm/pmp/ → c1_ProjectPlan.docx | Leader | baseline-v1.0
CI-02 | Project Workbook | Spreadsheet | deliverables/Sx/c2_SprintBacklog_Sx.xlsx | Leader | baseline-v1.0
CI-03 | Product Backlog & DoR | Document | pm/backlog/ | PO | baseline-v1.0
CI-04 | Release Plan & BAC | Document | pm/pmp/03-master-release-plan.md | PO + Leader | baseline-v1.0
CI-05 | Sprint Reports | Document | pm/sprints/Sx/ → c3_SprintReport_Sx.docx | Leader | per Sprint
CI-06 | Change Log & CR forms | Document | pm/change/ → c4_ChangeRequest_CR01.docx | PO | per CR
CI-07 | Source code | Code | app/ | Developers | tag per release
CI-08 | Database schema & seed | Database | app/db/ | Đạt | tag per release
CI-09 | Test cases & UAT script | Document | pm/sprints/Sx/, pm/uat/ | Developers | per Sprint
CI-10 | Hosting configuration (no secrets) | Config | app/README.md, host dashboard | Đạt | v1.0
6.5 Baselines and tags
Tag | When | Contents
baseline-v1.0 | After S1 submission | PMP v1.0, Backlog v1.0, Release Plan baseline, F1
baseline-v1.1 | After CCB approval of a CR | Updated backlog, Release Plan rebaseline, risk register
v1.0 | 12/11/2026 | Release 1.0 code + release notes

## TestCases_F1
Source: pm/sprints/S1/test-cases-F1.md
Version history
Version | Date | Author | Change
1.0 | 30/10/2026 | Hồ Du Tuấn Đạt (AI-assisted) | Test cases from F1 ACs; automated results from a real local run
Version history
TC | AC | Given | When (steps) | Then (expected) | Automated | Actual – local automated | Actual – hosted, manual
TC-F1-01 | US-01/AC-01 | Register page open | Submit valid name, new email, password Reader2026 | Account created as Customer, signed in, redirected home | E2E + INT | Pass (30/10) | TBD
TC-F1-02 | US-01/AC-02 | Customer x@y.com exists | Register with X@Y.COM | "Email is already registered" by email field; no new account | E2E + INT | Pass (30/10) | TBD
TC-F1-03 | US-01/AC-03 | Register page open | Submit not-an-email; then empty fields; then POST bypassing client | Field errors on client; server also rejects | E2E + INT | Pass (30/10) | TBD
TC-F1-04 | US-01/AC-04 | Register page open | Password abc1234 (7) then abcd1234 (8) | 7 rejected, 8 accepted | E2E + UNIT | Pass (30/10) | TBD
TC-F1-05 | US-02/AC-01 | Active account | Log in with correct credentials | Signed in; name and Log out shown | E2E + INT | Pass (30/10) | TBD
TC-F1-06 | US-02/AC-02 | Active account | Log in with wrong password; with unknown email | Same generic "Invalid email or password" | E2E + INT | Pass (30/10) | TBD
TC-F1-07 | US-02/AC-03 | Account locked by admin | Log in with correct credentials | "This account is locked…" | E2E + INT | Pass (30/10) | TBD
TC-F1-08 | US-02/AC-04 | Signed in | Click Log out; open /admin | Session ended; redirected to Login | E2E | Pass (30/10) | TBD
TC-F1-09 | US-02/AC-05 | Account e@x.com | Log in with E@X.COM | Signed in | E2E + INT + UNIT | Pass (30/10) | TBD
TC-F1-10 | US-03/AC-01 | Signed in as admin | Create account with role Customer | Appears in list, role Customer, Active | E2E + INT | Pass (30/10) | TBD
TC-F1-11 | US-03/AC-02 | Admin; another active account | Lock, then Unlock | Locked user cannot log in; after unlock can | E2E + INT | Pass (30/10) | TBD
TC-F1-12 | US-03/AC-03 | Signed in as admin | Click Lock on own row | "You cannot lock your own account" | E2E + INT | Pass (30/10) | TBD
TC-F1-13 | US-03/AC-04 | Admin; email exists | Create account with that email | Field error; no account | E2E + INT | Pass (30/10) | TBD
TC-F1-14 | US-03/AC-05 | User signed in in another browser | Admin locks that user; user reloads | User is signed out | E2E + INT | Pass (30/10) | TBD
TC-F1-15 | US-04/AC-01 | Not signed in | Open /admin/accounts | Redirect to /login?next=… | E2E | Pass (30/10) | TBD
TC-F1-16 | US-04/AC-02 | Signed in as Customer | Open /admin/accounts directly | HTTP 403 "Access denied" | E2E | Pass (30/10) | TBD
TC-F1-17 | US-04/AC-03 | Signed in as admin | Open /admin | Admin dashboard shown | E2E | Pass (30/10) | TBD
TC-F1-18 | US-04/AC-04 | Signed in as Customer | Look at header on any page | No Admin menu | E2E | Pass (30/10) | TBD
TC-F1-19 | NFR-01/AC-01 | New account saved | Inspect users.password_hash in DB | bcrypt hash $2…$10$…, not plain text | INT | Pass (30/10) | TBD
TC-F1-20 | NFR-01/AC-02 | Any form | Send invalid data bypassing client | Server rejects, nothing stored | INT | Pass (30/10) | TBD
TC-F1-21 | NFR-01/AC-03 | Register form | Name 101 chars; password 65 chars | Rejected (100 / 64 accepted) | UNIT | Pass (30/10) | TBD
TC-F1-22 | NFR-03/AC-01 | develop deployed | Open public URL | Home page over HTTPS | — | Not run (needs hosting) | TBD
TC-F1-23 | NFR-03/AC-02 | Site idle ≥ 15 min | Open URL | Responds; URL recorded | — | Not run (needs hosting) | TBD
TC-F1-24 | NFR-03/AC-03 | 17/11/2026 | Open URL | Online | — | Not run (needs hosting) | TBD
Summary (local automated)
ACs | Test cases | Executed | Pass | Fail | Not run
24 | 24 | 21 | 21 | 0 | 3 (NFR-03 hosting)